## P&L (hidden)
50/20/20/10
Project #:
|  |  |  | 50% | 20% | 20% | 10%
| PROJECTS BUDGET | [6 empty] | CONTRACT BUDGET - WARRANTY,SERVICE TAX INCL.
| Revenue | Budgeted Cost | Margin |  |  |  |  | Revenue | Budgeted Cost | Margin
Base Contract | 0 | 0 | 0 |  |  |  | TOTAL BASE CONTRACT | 175000 | 101127.02 | 73872.98
TOTAL BASE CONTRACT | 0 | 0 | 0 |  |  |  |  | CHANGE ORDERS
[8 empty] | Revenue | Budgeted Cost | Margin
| Revenue | Budgeted Cost | Margin |  |  |  | Total Change Order(s) Amount | 0 | 0 | 0
Change Orders | 0 | 0 | 0 |  |  |  |  | REVISED CONTRACT TOTAL
Total Change Order(s) Amount | 0 | 0 | 0 |  |  |  | Grand Total | 175000 | 101127.02 | 73872.98
Grand Total | 0 | 0 | 0 |  |  |  |  | Revenue | Actual Cost | Margin
[7 empty] | Margin Tracking | 175000 | 101127.02 | 73872.98
| Revenue | Actual Cost | Margin
Margin Tracking | 0 | 0 | 0
| 0 | 0 | 0 |  |  |  |  | Services/Warranty | Revenue | Budgeted Cost
Advertising
[8 empty] | Parts/Labor | 23707 | 13750
Graphics/Design
Cost Category | Revenue | Budget | Committed POs | Budget Remaining |  |  |  | Software License | 0
LED | 0 | 0 | 167523 | -167523 |  |  |  | Tax
Install | 0 | 0 | 94724 | -94724 |  |  |  | Total | 23707 | 13750
Electrical | 0 | 0 | 0 | 0
ANC Travel | 0 | 0 | 0 | 0
Structural Engineering | 0 | 0 | 60000 | -60000
Electrical Engineering | 0 | 0 | 7500 | -7500
CMS | 0 | 0 | 0 | 0
Parts/Labor | 0 | 0 | 0 | 0
Tax | 0 | 0 | 0 | 0
Bond | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0
BASE CONTRACT TOTAL | 0 | 0 | 329747 | -329747
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
CHANGE ORDER TOTAL | 0 | 0 | 0 | 0
0
GRAND TOTAL | 0 | 0 | 329747 | -329747

## PO's (hidden)
Number | Washington Commanders | Title | Original Contract Amount | 50/20/20/10
106963-001 | SEATTLE STRUCTURAL PS INC | Structural Engineering | 20000 | Structural Engineering
106963-002 | PENO ENGINEERING LLC | 2025-08-01 | 10000 | 50% | 20% | 20% | 10%
106963-003 | Fairplay Corporation | 2025-08-01 | 55237.5 | Courtside |  |  |  | CONTRACT BUDGET - WARRANTY,SERVICE TAX INCL.
106963-004 | HOIST SALES & SERVICE | Chain Hoists | 94724 | Install
106963-005 | LG ELECTRONICS ALABAMA INC | LED | 185556 |  |  |  |  | Revenue | Budgeted Cost | Margin
| LG ELECTRONICS ALABAMA INC | Shipping | 32148 |  |  |  | TOTAL BASE CONTRACT | 175000 | 101127.02 | 73872.98
106963-005 | Yaham Hong Kong Limited | LED | 151835 | LED |  |  |  | CHANGE ORDERS
106963-006 | OES Inc. | OES | 42912 | Scoring |  |  |  | Revenue | Budgeted Cost | Margin
106963-007 | SEATTLE STRUCTURAL PS INC | Structural Engineering | 40000 | Structural Engineering |  |  | Total Change Order(s) Amount | 0 | 0 | 0
106963-008 | PENO ENGINEERING LLC | Electrical Engineering | 7500 | Electrical Engineering |  |  |  | REVISED CONTRACT TOTAL
106963-009 | Lynnlink Visual Elements LLC | Processing | 15688 | LED |  |  | Grand Total | 175000 | 101127.02 | 73872.98
106963-010 | LG ELECTRONICS ALABAMA INC | Grand Hall
106963-011 | [7 empty] | Revenue | Actual Cost | Margin
106963-012 | [6 empty] | Margin Tracking | 175000 | 101127.02 | 73872.98
106963-013
106963-014
106963-015 | [7 empty] | Services/Warranty | Revenue | Budgeted Cost
106963-016 | [7 empty] | Advertising
106963-017 | [7 empty] | Parts/Labor | 23707 | 13750
106963-018 | [7 empty] | Graphics/Design
106963-019 | [7 empty] | Software License | 0
106963-020 | [7 empty] | Tax
106963-021 | [7 empty] | Total | 23707 | 13750
106963-022
106963-023
106963-024
106963-025
106963-026
106963-027
106963-028
106963-029
106963-030
106963-031
106963-032
106963-033
106963-034
106963-035
106963-036
106963-037
106963-038
106963-039
106963-040
106963-041
106963-042
106963-043
106963-044
106963-045
106963-046
106963-047
106963-048
106963-049
106963-050
106963-051
106963-052
106963-053
106963-054
106963-055
106963-056
106963-057
106963-058
106963-059
106963-060
106963-061
106963-062
106963-063
106963-064
106963-065
106963-066
106963-067
106963-068
106963-069
106963-070
106963-071
106963-072
106963-073
106963-074
106963-075
106963-076
106963-077
106963-078
106963-079
106963-080
106963-081
106963-082
106963-083
106963-084
106963-085
106963-086
106963-087
106963-088
106963-089
106963-090
106963-091
106963-092
106963-093
106963-094
106963-095
106963-096
106963-097
106963-098
106963-099
106963-100
106963-101
106963-102
106963-103
106963-104
106963-105
106963-106
106963-107
106963-108
106963-109
106963-110

## Cash Flow (hidden)
|  |  | Payment Terms: | 50/20/20/10
| Project #: |  | Payment Phases | Contract Signed | Product Shipping | Substantial Completion | Sign Off
| Contract Award Date | 2025-04-01 | Percentages | 50% | 20% | 20% | 10%
| Scheduled Completion Date | 2025-12-01
| Revenue | Expenses | Gross Profit | Gross Profit % | Budget Tracking (+/-)
| 0 | 0 | 0 | #DIV/0! | 0
Month |  |  |  |  | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY25 | FY26
Revenue |  | Amount | Date Submitted
1 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Revenue |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost of Rev |  | Budget | Committed Amt. | Paid | [12 empty] | FY25 | FY26
1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monthly Total COR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monthly Gross Profit |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Cash Flow |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Substantial Completion = DATE(YEAR([Product Shipping]),MONTH([Product Shipping])+1,DAY([Product Shipping]))
Sign Off = DATE(YEAR([Substantial Completion]),MONTH([Substantial Completion])+1,DAY([Substantial Completion]))

## Margin Analysis
Project Name: Cleveland Browns - Huntington Bank Field (Budgets)
2026-01-21
Revised By: JSR
LED Video Displays | Cost | Selling Price | Margin $ | Margin %
AV Display Controls & Scoreboards (Ross & OES) | 2000000 | 2500000 | 500000 | 20%
Cleveland Social North Left - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
Cleveland Social North Right - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
Cleveland Social South Left - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
Cleveland Social South Right - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
Dawg Pound Board - LED Display - 40'9" H x 344' W - 10mm (Outdoor) | 6848011.0548 | 8056483.5938 | 1208472.5391 | 15%
Endzone Video Board - LED Display - 40' H x 260' W - 10mm (Outdoor) | 5012790.4128 | 5897400.4856 | 884610.0728 | 15%
Exterior Video Board East - LED Display - 56'6" H x 224'1" W - 10mm (Outdoor) | 6278567.5818 | 7386550.0963 | 1107982.5144 | 15%
Exterior Video Board West - LED Display - 53'6" H x 211'2" W - 10mm (Outdoor) | 5570875.791 | 6553971.5188 | 983095.7278 | 15%
Grand Concourse Bar Board 01 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | 639818.1856 | 752727.2772 | 112909.0916 | 15%
Grand Concourse Bar Board 02 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | 639818.1856 | 752727.2772 | 112909.0916 | 15%
Grand Concourse Bar Board 04 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | 639818.1856 | 752727.2772 | 112909.0916 | 15%
Grand Concourse Bar Board 05 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | 639818.1856 | 752727.2772 | 112909.0916 | 15%
Interview Room - LED Display - 18' H x 32'9" W - 1.2mm (Outdoor) | 643093.038 | 756580.0447 | 113487.0067 | 15%
Locker Room Ceiling Video Board - LED Display - 4' H x 42' W - 1.2mm (Outdoor) | 206708.4765 | 243186.4429 | 36477.9664 | 15%
NE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
NE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
NW Tap Bar - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
NW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
NW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
SE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
SE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
SW Tap Bar - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
SW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
SW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | 75793.108 | 89168.3624 | 13375.2544 | 15%
Team Store Board - LED Display - 8' H x 40' W - 1.2mm (Outdoor) | 344514.1275 | 405310.7382 | 60796.6107 | 15%
Team Tunnel At Field - LED Display - 14' H x 16'9" W - 10mm (Outdoor) | 114585.6205 | 134806.6124 | 20220.9919 | 15%
| 31057532.8327 | 36685332.7443 | 5627799.9116 | 15.34%
TAX | 0% | 0
BOND | 0% | 0
SUB TOTAL (BID FORM) |  | 36685332.7443 | 5627799.9116 | 15.34%
36685328

## LED Cost Sheet
Outdoor | Type 1 | 10mm SMD | 6000 Nits
Outdoor | Type 2 | 10mm SMD Top | 6000 Nits | [13 empty] | 10% |  |  | 12 |  | 15%
Outdoor | Type 3 | 1.2mm SMD | 4000 Nits
LED Video Displays
|  |  |  | BID SPEC | Active Display Size (Feet) |  | Pixel Count |  |  | Square Feet | Quantity |  | LED NIT | LED Service | [7 empty] | LED | Total
OPTION | Issue | VENDOR | PRODUCT | PITCH | H | W | H |  | W | Per Screen | of Screens | Total SQ FT | Requirement | Requirement | Cost Sq. Ft | Display Cost | Sponsorship | Installation | Electrical | Shipping | Total Cost | Margin | Price | ANC Margin | Bond Cost | Total with Bond | Selling Sq. Ft | Shipping Sale Price
Cleveland Social North Left - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
Cleveland Social North Right - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
Cleveland Social South Left - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
Cleveland Social South Right - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
Dawg Pound Board - LED Display - 40'9" H x 344' W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 40.4555 | 344.4 | 1184.064 | x | 10080 | 13932.8811 | 1 | 13932.8811 | 6000 | Front / Rear | 195 | 2716911.8122 | 271691.1812 | 2089932.1632 | 1602281.3251 | 167194.5731 | 6848011.0548 | 15% | 8056483.5938 | 1208472.5391 | 120847.2539 | 8177330.8477 | 578.2353 | 196699.4977
[16 empty] | 3516003.5216 |  | 2458743.7214 | 1885036.8531 | 196699.4977
Endzone Video Board - LED Display - 40' H x 260' W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 39.36 | 259.12 | 1152 | x | 7584 | 10198.9632 | 1 | 10198.9632 | 6000 | Front / Rear | 195 | 1988797.824 | 198879.7824 | 1529844.48 | 1172880.768 | 122387.5584 | 5012790.4128 | 15% | 5897400.4856 | 884610.0728 | 88461.0073 | 5985861.4929 | 578.2353 | 143985.3628
[16 empty] | 2573738.3605 |  | 1799817.0353 | 1379859.7271 | 143985.3628
Exterior Video Board East - LED Display - 56'6" H x 224'1" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 56.8555 | 224.68 | 1664.064 | x | 6576 | 12774.2982 | 1 | 12774.2982 | 6000 | Front / Rear | 195 | 2490988.1556 | 249098.8156 | 1916144.735 | 1469044.2969 | 153291.5788 | 6278567.5818 | 15% | 7386550.0963 | 1107982.5144 | 110798.2514 | 7497348.3477 | 578.2353 | 180343.0339
[16 empty] | 3223631.7307 |  | 2254287.9236 | 1728287.4081 | 180343.0339
Exterior Video Board West - LED Display - 53'6" H x 211'2" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 53.5755 | 211.56 | 1568.064 | x | 6192 | 11334.437 | 1 | 11334.437 | 6000 | Front / Rear | 195 | 2210215.2172 | 221021.5217 | 1700165.5517 | 1303460.2563 | 136013.2441 | 5570875.791 | 15% | 6553971.5188 | 983095.7278 | 98309.5728 | 6652281.0916 | 578.2353 | 160015.5813
[16 empty] | 2860278.5164 |  | 2000194.7667 | 1533482.6545 | 160015.5813
Grand Concourse Bar Board 01 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 36.08 | 36.08 | 1056 | x | 1056 | 1301.7664 | 1 | 1301.7664 | 6000 | Front / Rear | 195 | 253844.448 | 25384.4448 | 195264.96 | 149703.136 | 15621.1968 | 639818.1856 | 15% | 752727.2772 | 112909.0916 | 11290.9092 | 764018.1863 | 578.2353 | 18377.8786
[16 empty] | 328504.5798 |  | 229723.4824 | 176121.3365 | 18377.8786
Grand Concourse Bar Board 02 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 36.08 | 36.08 | 1056 | x | 1056 | 1301.7664 | 1 | 1301.7664 | 6000 | Front / Rear | 195 | 253844.448 | 25384.4448 | 195264.96 | 149703.136 | 15621.1968 | 639818.1856 | 15% | 752727.2772 | 112909.0916 | 11290.9092 | 764018.1863 | 578.2353 | 18377.8786
[16 empty] | 328504.5798 |  | 229723.4824 | 176121.3365 | 18377.8786
Grand Concourse Bar Board 04 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 36.08 | 36.08 | 1056 | x | 1056 | 1301.7664 | 1 | 1301.7664 | 6000 | Front / Rear | 195 | 253844.448 | 25384.4448 | 195264.96 | 149703.136 | 15621.1968 | 639818.1856 | 15% | 752727.2772 | 112909.0916 | 11290.9092 | 764018.1863 | 578.2353 | 18377.8786
[16 empty] | 328504.5798 |  | 229723.4824 | 176121.3365 | 18377.8786
Grand Concourse Bar Board 05 - LED Display - 36' H x 36'8" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 36.08 | 36.08 | 1056 | x | 1056 | 1301.7664 | 1 | 1301.7664 | 6000 | Front / Rear | 195 | 253844.448 | 25384.4448 | 195264.96 | 149703.136 | 15621.1968 | 639818.1856 | 15% | 752727.2772 | 112909.0916 | 11290.9092 | 764018.1863 | 578.2353 | 18377.8786
[16 empty] | 328504.5798 |  | 229723.4824 | 176121.3365 | 18377.8786
Interview Room - LED Display - 18' H x 32'9" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 17.7 | 32.97 | 2880 | x | 5376 | 583.569 | 1 | 583.569 | 4000 | Front / Rear | 750 | 437676.75 | 43767.675 | 87535.35 | 67110.435 | 7002.828 | 643093.038 | 15% | 756580.0447 | 113487.0067 | 11348.7007 | 767928.7454 | 1296.4706 | 8238.6212
[16 empty] | 566405.2059 |  | 102982.7647 | 78953.4529 | 8238.6212
Locker Room Ceiling Video Board - LED Display - 4' H x 42' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 42.39 | 720 | x | 6912 | 187.5757 | 1 | 187.5757 | 4000 | Front / Rear | 750 | 140681.8125 | 14068.1813 | 28136.3625 | 21571.2113 | 2250.909 | 206708.4765 | 15% | 243186.4429 | 36477.9664 | 3647.7966 | 246834.2396 | 1296.4706 | 2648.1282
[16 empty] | 182058.8162 |  | 33101.6029 | 25377.8956 | 2648.1282
NE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
NE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
NW Tap Bar - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
NW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
NW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
SE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
SE Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
SW Tap Bar - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 4.425 | 29.83 | 720 | x | 4864 | 131.9977 | 1 | 131.9977 | 4000 | Front / Rear | 750 | 98998.3125 | 9899.8313 | 19799.6625 | 15179.7412 | 1583.973 | 145461.5205 | 15% | 171131.2006 | 25669.6801 | 2566.968 | 173698.1686 | 1296.4706 | 1863.4976
[16 empty] | 128115.4632 |  | 23293.7206 | 17858.5191 | 1863.4976
SW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
SW Wrap Around - LED Display - 8' H x 8'6" W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 8.635 | 1296 | x | 1408 | 68.7778 | 1 | 68.7778 | 4000 | Front / Rear | 750 | 51583.3312 | 5158.3331 | 10316.6662 | 7909.4441 | 825.3333 | 75793.108 | 15% | 89168.3624 | 13375.2544 | 1337.5254 | 90505.8878 | 1296.4706 | 970.9804
[16 empty] | 66754.8993 |  | 12137.2544 | 9305.2284 | 970.9804
Team Store Board - LED Display - 8' H x 40' W - 1.2mm (Outdoor) | Type 3 |  |  | 1.875mm | 7.965 | 39.25 | 1296 | x | 6400 | 312.6262 | 1 | 312.6262 | 4000 | Front / Rear | 750 | 234469.6875 | 23446.9688 | 46893.9375 | 35952.0187 | 3751.515 | 344514.1275 | 15% | 405310.7382 | 60796.6107 | 6079.6611 | 411390.3993 | 1296.4706 | 4413.5471
[16 empty] | 303431.3603 |  | 55169.3382 | 42296.4926 | 4413.5471
Team Tunnel At Field - LED Display - 14' H x 16'9" W - 10mm (Outdoor) | Type 1 |  |  | 10mm | 14.2155 | 16.4 | 416.064 | x | 480 | 233.1345 | 1 | 233.1345 | 6000 | Front / Rear | 195 | 45461.233 | 4546.1233 | 34970.1792 | 26810.4707 | 2797.6143 | 114585.6205 | 15% | 134806.6124 | 20220.9919 | 2022.0992 | 136828.7116 | 578.2353 | 3291.311
[16 empty] | 58832.1838 |  | 41141.3873 | 31541.7303 | 3291.311
[16 empty] | Sponsorship: | 1228723.6809

## Install (Base)
Project Name: Cleveland Browns - Huntington Bank Field (Budgets)
2026-01-21
Revised By: JSR
Linked Margin Assignment
|  | Install Margin | 20%
|  | Electrical Margin | 20%
|  | ANC Margin | 20%
|  | Engineering and Permits | 20%
AV Display Controls & Scoreboards (Ross & OES) | Height | Width | Total Sq. Ft | QTY
| 4.425 | 29.83 | 131.9977 | 1
Structural Materials: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
PRIMARY STRUCTURE & PIERS | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
FABRICATE CLADDING AND TRIM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
Structural Labor and LED Installation | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
INSTALL LED DISPLAYS | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
HEAVY EQUIPMENT | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
Electrical and Data - Materials and Subcontracting: | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
Electrical - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
Other Scope Item | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
Other Scope Item | 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
Project Management, General Conditions, Travel & Expenses | ANC Pricing | % Calculated | Other Multiplier if Needed |  |  |  | Total Cost | ANC Margin | Selling Price | Margin
Project Management | 0 | 0% | 0 | 0 | 0 | 4500 | 0 | 20% | 0 | 0
General Conditions | 0 | 0% | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Administrative & Legal | 0 | 0% | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Travel & Expenses - Linked from Worksheet | 0 |  | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
3rd Party Technician Support | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Payment Processing Systems (Texture, etc) | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Bim Modeling | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Spare Parts Management (Job Boxes, etc that PM's Purchase on site) | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Safety Plan Documents, Badging, Etc | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Graphics/Design | 0 | 0 | 0 | 0 | 0 |  | 0 | 33.3% | 0 | 0
Installation Contingency - Typically Included in Installation Sections | 0 |  |  | 0 | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Submittals, Engineering, and Permits | ANC Pricing | [5 empty] | Total Cost | Eng and Permit Margin | Selling Price | Margin
Structural Engineering - Specific Scope Detail? | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Structural Certification | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Electrical Engineering - Specific Scope Detail? | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Electrical Certification | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
Permits - Not included in subcontractor bid | 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Subtotal | [6 empty] | 0 |  | 0 | 0
Ross - Content Management System
|  |  |  | 0% | Contingency |  | Total Cost | ANC Margin | Selling Price | Margin
Materials | 1800000 | 0 | 0 | 0% | 0 | 4500 | 1800000 | 20% | 2250000 | 450000
Labor | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Shipping | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Related Scope Item | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 1800000 | 0 | 0 | 0 | 0 |  | 1800000 |  | 2250000 | 450000
Two Years Parts and Beyond Simple Component Replacement Warranty
| ANC Pricing |  |  | 0% |  |  | Total Cost | Margin | Selling Price | Margin
Labor Warranty - 5 Years - Beyond Simple Component Replacement | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Event Support - 3 Events | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Pre-Season Checks - 2 Seasons | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Display Cleaning - XX Cleanings | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Other Service Elements | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Scoring, Signage and Misc. Expenses
|  |  |  | 0% | Contingency |  | Total Cost | ANC Margin | Selling Price | Margin
Materials | 200000 | 0 | 0 | 0% | 0 | 4500 | 200000 | 20% | 250000 | 50000
Labor | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Shipping | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
Related Scope Item | 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 20% | 0 | 0
SUBTOTAL | 200000 | 0 | 0 | 0 | 0 |  | 200000 |  | 250000 | 50000

## Resp Matrix - ROM Example (hidden)
Project: | ROM Proposal
Date: | 2025-08-12
| Administrative | YES | NO
| Physical Installation | ANC | Purchaser
| ANC assumes all base building structure is to be provided by others or is existing and is of sufficient capacity to support the proposed display systems. | Include Statement
| ANC has included removal and disposal of any existing signage and display systems that would be replaced by those systems that are part of this ROM proposal. | Include Statement
| ANC assumes reasonable access will be provided to the installation team and any unknown site conditions such as lane closures, site protection, permitting, etc is not currently in this ROM Proposal. | Include Statement
| ANC assumes all base building structure is to be provided by others or is existing and is of sufficient capacity to support the proposed display systems. Any shoring or modifications to existing structure could result in additional cost. | Include Statement
| Electrical & Data Installation | ANC | Purchaser
| ANC assumes primary power feed will be provided by others or is existing, within 5' of the display location with sufficient amps for ANC proposed display(s); typically 208v 3-phase. | Include Statement
| ANC assumes all secondary power distribution, which may include breaker panels, disconnects, pathway, etc may be included in this ROM Estimate | Include Statement
| ANC assumes all data pathway is provided by others or is existing, but ANC will provide data cabling and labor to pull cable form control location to the display(s). |  | x
| ANC assumes all data pathways and cables are provided and existing. Any modifications or additional cabling pulls required could result in additional cost. | Include Statement
| Control System | ANC | Purchaser
| ANC has provided display processors only. Content creation studio and content delivery system is not included at this time. | Include Statement
| Training | ANC | Column1
| ANC will provide appropriate on-site operation and Maintenance Training | Included Statement
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
Perform two (2) days of control system operation.
| Perform final systems testing and commissioning. | X
| Project Close- Out | ANC | Column1
Site walk thru to conduct final inspection of punch list items with ANC
| Completion of punch list items | X
| General Conditions | YES | No
| ANC has provided a parts only warranty, excluding on-site labor, on all products consistent with the factory supplier and/or 3rd party vendor. Warranty Terms and Conditions to be defined. | Included Statement
| ANC has included installation pricing with Union labor rates and/or prevailing wage negotiation. |  | X
| ANC has not included bonding of any kind. | Included Statement
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | Included Statement
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | Included Statement
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance. ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | Included Statement

## Resp Matrix-Indoor Wall Example (hidden)
Project: | Whatnot Lobby
Date: | 2022-08-24
| Administrative | ANC | Purchaser
| Provide accurate architectural, structural engineering, and electrical drawings or information, including exploratory surveys to confirm existing conditions if necessary. |  | X
| Provide Payment and Performance Bond. | NA |  | Editable
| All required zoning , building, street or sidewalk closure permits, and associated costs, as required. | NA |  | Editable
| Shipping of all equipment to site. | X
| Receive, unload, and inspect all new equipment upon delivery. | X
| Provide safe storage of video equipment and control equipment in a safe, dry and secure location until installation, if required. |  | X
| Unobstructed access to equipment and control room throughout installation, until equipment is 100% operational. |  | X
| Engineering & Submittals | ANC | Purchaser
| Customer is responsible to ensure the existing structure/building is adequate, including, but not limited to, providing sealed engineering and calculations, as-builts, and other information, documentation, or enabling of exploratory work as may be required for ANC's Engineer to adequately design the display system and it's attachment to the base building. ANC assumes base building defined as plywood "backer" or similar condition. |  | X
| Provide mechanical drawings, electrical drawings, shop drawings, and equipment locations for new equipment. | X
| Engineering and certification for new equipment attachment design | X
| Provide approval of all mechanical drawings, electrical drawings, shop drawings, equipment locations, color renderings, and ad copy layouts for new equipment. |  | X
| Responsible to ensure sufficient structural integrity at points of attachment, including any modifications, additions or alterations to base building construction, as required. |  | X
| Demolition, Removal & Site Cleanup | ANC | Purchaser
| Removal of existing equipment and structural components, as required. | NA |  | Editable
| Disposal of existing equipment and structural components, as required. | NA |  | Editable
| Post installation site clean-up. | X
| Physical Installation | ANC | Purchaser
| Fabricate, deliver, and install support structure and appropriate backing for all displays, including hardware, shims and miscellaneous materials as required. | X
| Provide & Install LED components. | X
| Provide all required Floor/Site Protection, if required. |  | X | Editable
| Provide camera ready artwork for ad panels, and logos at time of order, if required. |  | X
| Electrical & Data Installation | ANC | Purchaser
| Submit electrical engineering drawings | X
| Provide (and install, if required) primary power feed within 5' of the display location with sufficient amps for ANC proposed display(s); typically 208v 3-phase. |  | X | Editable
| Provide secondary electrical panels and/or remote power control, if required. |  | X | Editable
| Installation of secondary electrical panels and/or remote power control, if required. Including all conduit, wire, and low voltage conduit & wire as may be required for the remote power control. |  | X | Editable
| Provide & Install all branch circuits necessary to LED display(s) and 120V 1-phase servicing outlets in the vicinity of the display location (if necessary). Exact locations to be coordinated with ANC and electrical contractor. |  | X | Editable
| Furnish signal cables as specified by ANC. | X |  | Editable
| Provide and install signal cable conduit, with pull string, from control location to all Equipment locations/signal termination points, as delineated in the electrical and signal drawings. |  | X | Editable
| Labor to pull signal cable (and remove existing cable), if required. | X |  | Editable
| Terminate signal cable at control system equipment and display equipment, if required. | X |  | Editable
| Mount and install data patch panel in control location and display location, if required. | X |  | Editable
| Provide high speed internet connection to control room equipment. |  | X
| Power outlets on clean dedicated circuit(s) for all control equipment required per electrical engineering within control room location. |  | X
| Control System | ANC | Purchaser
| Provide climate controlled control room for all control equipment and processing. Normal operating temperature should be between 65 and 75 degrees Fahrenheit. Normal operating humidity should be less than 80 percent non condensing. |  | X
| Supply static IP address five (5) days prior to installation. |  | X
| Provide and install signal cable conduit, with pull string, from production control location to display for LiveSync control, should remote location be desired. |  | X | Editable
| Labor to pull signal cable for LiveSync or other owner supplied control, if required. | X |  | Editable
| Third party application fees as required by the customer, i.e. RSS Feeds, etc. |  | X
| Provide computer(s) for control software. | X
| Set-up, and testing of all control equipment. | X
| Training | ANC | Purchaser
| Provide list of personnel for training five (5) days in advance. |  | X
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
| Perform two (2) days of control system operation. |  | X
| Perform final systems testing and commissioning. | X
| Project Close- Out | ANC | Purchaser
| Site walk thru to conduct final inspection of punch list items with ANC |  | X
| Completion of punch list items | X
| Project Specific Notes | YES | NO
| ANC has provided a (5) year warranty on all LED parts. | X |  | Editable
| ANC has not provided on site labor during the warranty period as part of this proposal. ANC will train facility staff to perform basic troubleshooting and simple component replacement. ANC will deploy an authorized service technician to perform all escalated service needs at and invoice for costs incurred. | X |  | Editable
| ANC has provided studio graphic creation hours as part of this proposal. |  | X | Editable
| ANC has not included a video scaler as part of the control system package. This would be required for any event utilizing live camera shoots. |  | X | Editable
| ANC has included installation pricing with Union labor rates. |  | X | Editable
| ANC has included applicable bonds. |  | X | Editable
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | X
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | X
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance . ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | X

## Resp Matrix - Pitch Example (hidden)
Project: | Portland Timbers
Date: | 2022-08-29
| Administrative | ANC | Purchaser
| Provide Payment and Performance Bond. | NA |  | Editable
| All required zoning , building, street or sidewalk closure permits, and associated costs, as required. | NA |  | Editable
| Shipping of all equipment to site. | X
| Receive, unload, and inspect all new equipment upon delivery. | X
| Provide safe storage of video equipment and control equipment in a safe, dry and secure location until installation, if required. |  | X
| Unobstructed access to equipment and control room throughout installation, until equipment is 100% operational. |  | X
| Engineering & Submittals | ANC | Purchaser
| Provide mechanical drawings, electrical drawings, shop drawings, etc as relevant to new equipment. | X
| Engineering and certification for new equipment attachment design | NA
| Provide approval of all mechanical drawings, electrical drawings, shop drawings, equipment locations, color renderings, and ad copy layouts for new equipment. |  | X
| Responsible to ensure sufficient structural integrity at points of attachment, including any modifications, additions or alterations to base building construction, as required. | NA
| Physical Installation and Services | ANC | Purchaser
| Provide and Deliver LED Displays and Novastar Display Processors. | X |  | Editable
| Utilize Existing Storage Carts/Racks and all tools and components related to storage. |  | X | Editable
| Column1 | Column2 | Column3
| Initial Setup and testing of LED components, including new Novastar Display processing. | X
| Provide all required Field/Site Protection, if required. |  | X | Editable
| Post installation site clean-up. Disposal/Use of shipping materials. |  | X
| Electrical & Data Installation | ANC | Purchaser
| Submit electrical engineering drawings | X
| Provide (and install, if required) primary power feed at the display location with sufficient amps for ANC proposed display(s). |  | X | Editable
| Provide secondary electrical panels and/or remote power control, if required. |  | X | Editable
| Installation of secondary electrical panels, branch circuits and/or remote power control, if required. Including all conduit, wire, and low voltage conduit & wire as may be required for the remote power control. |  | X | Editable
| Furnish signal cables as specified by ANC. |  | X | Editable
| Provide and install signal cable conduit, with pull string, from control location to all Equipment locations/signal termination points, as delineated in the electrical and signal drawings. |  | X | Editable
| Labor to pull signal cable (and remove existing cable), if required. |  | X | Editable
| Terminate signal cable at control system equipment and display equipment, if required. |  | X | Editable
| Mount and install data patch panel in control location and display location, if required. |  | X | Editable
| Provide high speed internet connection to control room equipment. |  | X
| Power outlets on clean dedicated circuit(s) for all control equipment required per electrical engineering within control room location. |  | X
| Control System | ANC | Purchaser
| Provide climate controlled control room for all control equipment and processing. Normal operating temperature should be between 65 and 75 degrees Fahrenheit. Normal operating humidity should be less than 80 percent non condensing. |  | X
| Supply static IP address five (5) days prior to installation. |  | X
| Provide and install signal cable conduit, with pull string, from production control location to display for LiveSync control, should remote location be desired. |  | X | Editable
| Labor to pull signal cable for owner supplied control, if required. |  | X | Editable
| Third party application fees as required by the customer, i.e. RSS Feeds, etc. |  | X
| Provide computer(s) for control software. |  | X
| Set-up, and testing of all control equipment. ANC to coordinate integration of processors with existing control system. | X | X
| Training | ANC | Purchaser
| Provide list of personnel for training five (5) days in advance. |  | X
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
| Perform one (1) days of processing/control system operation. | X
| Perform final systems testing and commissioning. | X | X
| Project Close- Out | ANC | Purchaser
| Site walk thru to conduct final inspection of punch list items with ANC |  | X
| Completion of punch list items | X
| Project Specific Notes | YES | NO
| ANC has provided a three (3) year warranty on all LED parts. | X |  | Editable
| ANC has not provided on site labor during the warranty period as part of this proposal. ANC will train facility staff to perform basic troubleshooting and simple component replacement. ANC will deploy an authorized service technician to perform all escalated service needs at and invoice for costs incurred. | X |  | Editable
| ANC has provided studio graphic creation hours as part of this proposal. |  | X | Editable
| ANC has included a video scaler as part of the control system package. This would be required for any event utilizing live camera shoots. |  | X | Editable
| ANC has included installation pricing with Union labor rates. |  | X | Editable
| ANC has included applicable bonds. |  | X | Editable
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | X
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | X
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance . ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | X

## Margin Analysis (CMS Only) (hidden)
Project Name: Cleveland Browns - Huntington Bank Field (Budgets)
2026-01-21
Revised By: JSR
LED Video Displays | Cost | Selling Price | Margin $ | Margin %
Cleveland Social North Left - LED Display - 4' H x 30' W - 1.2mm (Outdoor) | 145461.5205 | 171131.2006 | 25669.6801 | 15%
Structural Materials: | 0 | 0 | 0 | #DIV/0!
Structural Labor and LED Installation | 0 | 0 | 0 | #DIV/0!
Electrical and Data - Materials and Subcontracting: | 0 | 0 | 0 | #DIV/0!
Project Management, General Conditions, Travel & Expenses | 0 | 0 | 0 | #DIV/0!
Graphics/Design | 0 | 0 | 0 | 0%
Submittals, Engineering, and Permits | 0 | 0 | 0 | #DIV/0!
Content Manangement System Equipment, Installation, and Commissioning
Two Years Parts and Beyond Simple Component Replacement Warranty | 0 | 0 | 0 | 0%
| 145461.5205 | 171131.2006 | 25669.6801 | 15%
TAX | 2% | 3422.624
BOND | 1.33% | 2276.045
SUB TOTAL (BID FORM) |  | 176829.8696 | 25669.6801 | 14.52%
Alternates - Add to Cost Above | Cost | Selling Price | Margin $ | Margin %
Alternate #1: Additional Animation Graphics | 5000 | 10000 | 5000 | 50%
| 0 | 0 | 0 | #DIV/0!
| 0 | 0 | 0 | #DIV/0!

## Travel (ANC) (hidden)
vSOFT
Expenses | Week | 1 | TOTALS |  |  | MASTER TRAVEL KEY
[6 empty] | City | Westchester, NY
City |  | Westchester, NY |  |  |  | Project | Community College
Project |  | Community College |  |  |  | Building | Marquee
Building |  | Marquee |  |  |  | Flight / Train Cost | 600
Stage of Job |  | Install |  |  |  | Car Rental | 125
Number of People |  | 2 |  |  |  | Taxi / Bus/ Limo | 35
Days of Travel |  | 3 |  |  |  | Gas | 30
Night of Travel |  | 4 |  |  |  | Per Diem/Day | 75
Airfare/Rail |  | 1200 | 1200 |  |  | Hotel/Night | 185
Car Rental |  | 750 | 750
Taxi/Bus/Limo |  | 210 | 210
Mileage/Gas |  | 180 | 180 |  |  | Total Project Travel | 7845
Per Diem |  | 450 | 450
Lodging/Room |  | 1480 | 1480
Daily Totals |  | 4270 | 4270
Community College
Expenses | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | TOTALS
City | [9 empty] | Total Number of Travel Days (Should Coinicde with PM on site weeks)
Project
Building
Stage of Job |  | Sales | Demolition | Primary | Secondary | Display | CMS | Closeout
Number of People |  | 1 | 1 | 0 | 1 | 1 | 1 | 0
Days of Travel |  | 1 | 3 | 0 | 3 | 4 | 1 | 0 |  | 12
Night of Travel |  | 1 | 2 | 0 | 2 | 3 | 1 | 0
Airfare/Rail |  | 600 | 600 | 0 | 600 | 600 | 600 | 0 | 3000
Car Rental |  | 125 | 375 | 0 | 375 | 500 | 125 | 0 | 1500
Taxi/Bus/Limo |  | 35 | 105 | 0 | 105 | 140 | 35 | 0 | 420
Mileage/Gas |  | 30 | 90 | 0 | 90 | 120 | 30 | 0 | 360
Per Diem |  | 75 | 225 | 0 | 225 | 300 | 75 | 0 | 900
Lodging/Room |  | 185 | 370 | 0 | 370 | 555 | 185 | 0 | 1665
Daily Totals |  | 1050 | 1765 | 0 | 1765 | 2215 | 1050 | 0 | 7845