## AIA Cash Flow Template (hidden)
| Project Name |  | Payment Terms: | Example: AIA/ Progress Pay, 50/30/20, 30/30/30/10, 40/40/20
| Project No. |  | Payment Phases | Contract Signed | Product Shipping | Substantial Completion | Sign Off
| Contract Award Date | 2023-09-01 | Percentages | 40% | 30% | 20% | 10%
| Project Start Date | 2023-11-01
| Scheduled Completion Date | 2023-12-15
| Revenue | Expenses | Gross Profit | Gross Profit % | Budget Tracking (+/-)
| 1128307.8104 | 775965.5882 | 352342.2222 | 31.23% | 0
Month |  |  |  | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | FY23 | FY24
Revenue |  | Amount | Date Submitted
1 | Submittals | 101666.6667 |  |  | 40666.6667 |  |  |  |  | 30500 |  |  | 20333.3333 | 10166.6667 |  |  | 101666.6667 | 203333.3333
2 | LED / Technology Equipment & Processing | 396975 |  |  | 158790 |  |  |  |  | 119092.5 |  |  | 79395 | 39697.5 |  |  | 396975 | 793950
3 | Shipping | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
4 | Structural Installation - Materials | 7133.3333 |  |  | 2853.3333 |  |  |  |  | 2140 |  |  | 1426.6667 | 713.3333 |  |  | 7133.3333 | 14266.6667
5 | Structural Installation - Labor | 156613.3333 |  |  | 62645.3333 |  |  |  |  | 46984 |  |  | 31322.6667 | 15661.3333 |  |  | 156613.3333 | 313226.6667
6 | Heavy Equipment Rentals | 11666.6667 |  |  | 4666.6667 |  |  |  |  | 3500 |  |  | 2333.3333 | 1166.6667 |  |  | 11666.6667 | 23333.3333
7 | Mechanical/ Electric Installation - Labor | 275458.8889 |  |  | 110183.5556 |  |  |  |  | 82637.6667 |  |  | 55091.7778 | 27545.8889 |  |  | 275458.8889 | 550917.7778
8 | Mechanical/ Electric Installation - Material | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
9 | Structural Engineering | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
10 | Electrical Engineering | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
11 | Misc. Electrical Material (Panels, Etc.) | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
12 | Misc. Installation Material (Hoists, Etc.) | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
13 | CMS - Hardware | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
14 | CMS - Labor | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
15 | Scoring Equipment (OES, Etc.) | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
16 | SG&A - Project Management Fees | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
17 | Travel | 33333.3333 |  |  | 13333.3333 |  |  |  |  | 10000 |  |  | 6666.6667 | 3333.3333 |  |  | 33333.3333 | 66666.6667
18 | Service & Warranty Requirements | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
19 | Graphic Design Services | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 0 | 0 |  |  | 0 | 0
20 | Bond | 74077.925 |  |  | 29631.17 |  |  |  |  | 22223.3775 |  |  | 14815.585 | 7407.7925 |  |  | 74077.925 | 148155.85
21 | Taxes | 71382.6632 |  |  | 28553.0653 |  |  |  |  | 21414.799 |  |  |  | 7138.2663 |  |  | 57106.1306 | 114212.2611
Total Revenue |  | 1128307.8104 |  | 0 | 451323.1242 | 0 | 0 | 0 | 0 | 338492.3431 | 0 | 0 | 211385.0294 | 112830.781 | 0 | 0 | 451323.1242 | 662708.1536
Cost of Rev |  | Starting Amount | PO Number
1 | Submittals | 91500 |  |  |  | 36600 | 27450 | 18300 |  | 9150 |  |  |  |  | 9150 |  | 100650 | 201300
2 | LED / Technology Equipment & Processing | 103220 |  |  |  | 41288 |  |  |  |  | 30966 |  |  | 20644 | 10322 |  | 103220 | 206440
3 | Shipping | 0 | [8 empty] | 0 | [5 empty] | 0 | 0
4 | Structural Installation - Materials | 6420 |  |  |  | 2568 | 1926 | 1284 |  | 642 |  |  |  |  | 642 |  | 7062 | 14124
5 | Structural Installation - Labor | 140952 |  |  |  | 56380.8 | 42285.6 | 28190.4 |  | 14095.2 |  |  |  |  | 14095.2 |  | 155047.2 | 310094.4
6 | Heavy Equipment Rentals | 10500 |  |  |  | 4200 | 3150 | 2100 |  | 1050 |  |  |  |  | 1050 |  | 11550 | 23100
7 | Mechanical/ Electric Installation - Materials | 247913 |  |  |  | 99165.2 | 74373.9 | 49582.6 |  | 24791.3 |  |  |  |  | 24791.3 |  | 272704.3 | 545408.6
8 | Mechanical/ Electric Installation - Labor | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
9 | Structural Engineering | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
10 | Electrical Engineering | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
11 | Misc. Electrical Material (Panels, Etc.) | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
12 | Misc. Installation Material (Hoists, Etc.) | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
13 | CMS - Hardware | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
14 | CMS - Labor | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
15 | Scoring Equipment (OES, Etc.) | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
16 | SG&A - Project Management Fees | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
17 | Travel | 30000 |  |  |  | 12000 | 9000 | 6000 |  | 3000 |  |  |  |  | 3000 |  | 33000 | 66000
18 | Service & Warranty Requirements | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
19 | Graphic Design Services | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 |  | 0 | 0
20 | Bond | 74077.925 |  |  |  | 29631.17 | 22223.3775 | 14815.585 |  | 7407.7925 |  |  |  |  | 7407.7925 |  | 81485.7175 | 162971.435
21 | Taxes | 71382.6632 |  |  |  | 28553.0653 | 21414.799 | 14276.5326 |  | 7138.2663 |  |  |  |  | 7138.2663 |  | 78520.9295 | 157041.859
Monthly Total COR |  | 775965.5882 |  | 0 | 0 | 310386.2353 | 201823.6765 | 134549.1176 | 0 | 67274.5588 | 30966 | 0 | 0 | 20644 | 77596.5588 | 0 | 512209.9117 | 331030.2353
Monthly Gross Profit |  |  |  | 0 | 451323.1242 | -310386.2353 | -201823.6765 | -134549.1176 | 0 | 271217.7843 | -30966 | 0 | 211385.0294 | 92186.781 | -77596.5588 | 0 | 270791.1308 | 541582.2615
Project Cash Flow |  |  |  | 0 | 451323.1242 | 140936.8889 | -60886.7876 | -195435.9052 | -195435.9052 | 75781.8791 | 44815.8791 | 44815.8791 | 256200.9085 | 348387.6896 | 270791.1308 | 270791.1308
Formulas:
Product Shipping = DATE(YEAR([Contract Signed]),MONTH([Contract Signed])+1,DAY([Contract Signed]))
Substantial Completion = DATE(YEAR([Product Shipping]),MONTH([Product Shipping])+1,DAY([Product Shipping]))
Sign Off = DATE(YEAR([Substantial Completion]),MONTH([Substantial Completion])+1,DAY([Substantial Completion]))

## Budget Control (hidden)
Project Name | WVU | Base Contract |  | Tracking
Salesforce Opp. # | 107072 | Revenue | 467811.75 | Revenue | 467811.75
|  | Budget | 473808.1782 | Committed Cost | 338688
|  | Margin | -5996.4282 | Left Over Budget | 15620.1782
|  |  |  | Margin Tracking | 9623.75
[5 empty] | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets | Quotes/Budgets
| Professional Services | Revenue | Budget | PO Amount | Seattle Structure | Peno | ANC | [6 empty] | Left Over Budget
| Structural Engineering | 467811.75 | 55000 | 0 | [9 empty] | 55000
| Electrical Engineering |  | 21500 | 8500 | [9 empty] | 13000
| Permit Expediter |  | 0 | 0 | [9 empty] | 0
| Travel |  | 30000 | 0 |  | 7500 | [7 empty] | 22500
| Other |  | 0 | 0 | [9 empty] | 0
| Technology |  |  |  | HSS | Lighthouse | OES | Satern | Square V | Trans Lux
| CMS Hardware |  | 0 | 0 | [9 empty] | 0
| Hoist |  | 0 | 0 | [9 empty] | 0
| LED |  | 88220 | 133288 | [9 empty] | -45068
| AIO |  | 0 | 0 | [9 empty] | 0
| LED Processing |  | 15000 | 65400 | [9 empty] | -50400
| Audio Hardware |  | 0 | 0 | [9 empty] | 0
| Broadcast Hardware |  | 0 | 0 | [9 empty] | 0
| Lighting Hardware |  | 0 | 0 | [9 empty] | 0
| Misc Equipment |  | 0 | 0 | [9 empty] | 0
| Shipping |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Install |  |  |  | HSS | EST
| Demolition |  | 22482 | 0 | [9 empty] | 22482
| Primary Structure Fabrication |  | 0 | 0 | [9 empty] | 0
| Secondary Structure Fabrication |  | 5725.59 | 0 | [9 empty] | 5725.59
| Trim/Cladding Fabrication |  | 0 | 0 |  | 50000 | [7 empty] | -50000
| Signage Fabrication |  | 0 | 0 | [9 empty] | 0
| Hoist Install |  | 0 | 0 | [9 empty] | 0
| Primary Structure Install |  | 0 | 0 | [9 empty] | 0
| Secondary Structure Install |  | 19980 | 0 | [9 empty] | 19980
| Trim/Cladding Install |  | 0 | 0 |  |  | 25000 | [6 empty] | -25000
| Signage Install |  | 0 | 0 | [9 empty] | 0
| LED Install |  | 59940 | 81000 | [9 empty] | -21060
| Equipment |  | 10500 | 0 | [9 empty] | 10500
| Installer Travel |  | 0 | 0 | [9 empty] | 0
| Screen Cleaning |  | 0 | 0 | [9 empty] | 0
| Scoring Install |  | 0 | 15000 | [9 empty] | -15000
| CMS Integration |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Electrical / Mechanical |  |  |  | RCR | Lyntec | Anixter
| Electrical Install |  | 0 | 35000 |  | 35000 | [7 empty] | -70000
| Low Voltage Install |  | 0 | 0 | [9 empty] | 0
| Electrical Panels |  | 0 | 0 | [9 empty] | 0
| Low Voltage Materials |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Non-Install |  |  |  | ANC
| Project Management |  | 0 | 0 | [9 empty] | 0
| General Conditions |  | 0 | 0 | [9 empty] | 0
| Admin / Legal |  | 0 | 0 | [9 empty] | 0
| Initial Warranty |  | 0 | 0 | [9 empty] | 0
| Year 1 Ops |  | 0 | 0 | [9 empty] | 0
| Graphics |  | 0 | 500 | [9 empty] | -500
| Extended Warranty |  | 0 | 0 | [9 empty] | 0
| Marketing Commitment |  | 0 | 0 | [9 empty] | 0
| Sales Gift |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Bond |  | 74077.925 | 0 | [9 empty] | 74077.925
| Tax |  | 71382.6632 | 0 | [9 empty] | 71382.6632
| Total | 467811.75 | 473808.1782 | 338688 | [9 empty] | 17620.1782 | Contract Margin Differential
| Change Orders | Revenue | Budget | PO Amount | Seattle Structure | Peno | ANC | [6 empty] | Left Over Budget
| Other |  | 0 | 0 | 0 | [8 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | 2000 | [8 empty] | -2000
| Other |  | 0 | 0 | [9 empty] | 0
| Other |  | 0 | 0 | [9 empty] | 0
| Change Order Total | 0 | 0 | 0 | [9 empty] | -2000 | Change Order Margin Differential
| Grand Total | 467811.75 | 473808.1782 | 338688 | [9 empty] | 15620.1782

## PO's (hidden)
Number | Contract Company | Title | Original Contract Amount | Cost Category | Invoiced
107072-001 | Lighthouse | LED | 133288 | LED
107072-002
107072-003 | test |  | 8500 | Electrical Engineering
107072-004
107072-005
107072-006
107072-007
107072-008
107072-009 | test | test | 26000 | LED Install
107072-010
107072-011
107072-012
107072-013 | test | test | 15000 | Scoring Install
107072-014
107072-015
107072-016 | test | test | 35000 | Electrical Install
107072-017
107072-018
107072-019 | test | test | 55000 | LED Install
107072-020
107072-021
107072-022
107072-023
107072-024
107072-025 | test | test | 65400 | LED Processing
107072-026
107072-027
107072-028
107072-029
107072-030 | help | help more | 500 | Graphics
107072-031
107072-032
107072-033
107072-034
107072-035
107072-036
107072-037
107072-038
107072-039
107072-040
107072-041
107072-042
107072-043
107072-044
107072-045
107072-046
107072-047
107072-048
107072-049
107072-050
107072-051
107072-052
107072-053
107072-054
107072-055
107072-056
107072-057
107072-058
107072-059
107072-060
107072-061
107072-062
107072-063
107072-064
107072-065
107072-066
107072-067
107072-068
107072-069
107072-070
107072-071
107072-072
107072-073
107072-074
107072-075
107072-076
107072-077
107072-078
107072-079
107072-080
107072-081
107072-082
107072-083
107072-084
107072-085
107072-086
107072-087
107072-088
107072-089
107072-090
107072-091
107072-092
107072-093
107072-094
107072-095
107072-096
107072-097
107072-098
107072-099
107072-100
107072-101
107072-102
107072-103
107072-104
107072-105
107072-106
107072-107
107072-108
107072-109
107072-110

## Cash Flow (hidden)
| Project Name |  | Payment Terms: | Example: AIA/ Progress Pay, 50/30/20, 30/30/30/10, 40/40/20
| Project No. |  | Payment Phases | Contract Signed | Product Shipping | Substantial Completion | Sign Off
| Contract Award Date | 2024-01-26 | Percentages | 40% | 30% | 20% | 10%
| Scheduled Completion Date | 2024-07-31 | AIA
| Revenue | Expenses | Gross Profit | Gross Profit % | Budget Tracking (+/-)
| 1111641.1437 | 760965.5882 | 350675.5556 | 31.55% | 0
Month |  |  |  | 2024-01-26 | 2024-02-26 | 2024-03-26 | 2024-04-26 | 2024-05-27 | 2024-06-27 | 2024-07-27 | 2024-08-27 | 2024-09-27 | 2024-10-27 | 2024-11-27 | 2024-12-27 | 2025-01-27 | FY24
Revenue |  | Amount | Date Submitted
1 | Submittals |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
2 | LED / Technology Equipment & Processing | 396975 |  | 0 | 0 | 0 | 0 | 357277.5 | 0 | 0 | 39697.5 | [5 empty] | 396975
3 | Shipping | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
4 | Structural Installation - Materials | 7133.3333 |  | 0 | 0 | 0 | 0 | 0 | 2140 | 4280 | 713.3333 | [5 empty] | 7133.3333
5 | Structural Installation - Labor | 156613.3333 |  | 0 | 0 | 0 | 0 | 0 | 46984 | 93968 | 15661.3333 | [5 empty] | 156613.3333
6 | Heavy Equipment Rentals | 11666.6667 |  | 0 | 0 | 0 | 0 | 0 | 3500 | 7000 | 1166.6667 | [5 empty] | 11666.6667
7 | Mechanical/ Electric Installation - Labor | 275458.8889 |  | 0 | 0 | 0 | 0 | 110183.5556 | 0 | 0 | 27545.8889 | [5 empty] | 137729.4444
8 | Mechanical/ Electric Installation - Material | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
9 | Structural Engineering | 61111.1111 |  | 0 | 0 | 18333.3333 | 36666.6667 | 0 | 0 | 0 | 6111.1111 | [5 empty] | 61111.1111
10 | Electrical Engineering | 23888.8889 |  | 0 | 0 | 7166.6667 | 14333.3333 | 0 | 0 | 0 | 2388.8889 | [5 empty] | 23888.8889
11 | Misc. Electrical Material (Panels, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
12 | Misc. Installation Material (Hoists, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
13 | CMS - Hardware | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
14 | CMS - Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
15 | Scoring Equipment (OES, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
16 | SG&A - Project Management Fees | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
17 | Travel | 33333.3333 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | 3333.3333 | [5 empty] | 33333.3333
18 | Service & Warranty Requirements | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
19 | Graphic Design Services | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
20 | Bond | 74077.925 |  | 0 | 0 | 66670.1325 | 0 | 0 | 0 | 0 | 7407.7925 | [5 empty] | 74077.925
21 | Taxes | 71382.6632 |  | 0 | 0 | 0 | 0 | 0 | 21414.799 | 42829.5979 | 7138.2663 | [5 empty] | 71382.6632
Total Revenue |  | 1111641.1437 |  | 0 | 0 | 92170.1325 | 51000 | 467461.0556 | 84038.799 | 168077.5979 | 111164.1144 | 0 | 0 | 0 | 0 | 0 | 973911.6993
Cost of Rev |  | Starting Amount | PO Number
1 | Submittals | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
2 | LED / Technology Equipment & Processing | 103220 |  | 0 | 41288 | 0 | 30966 | 0 | 0 | 20644 | 0 | 10322 |  |  |  |  | 103220
3 | Shipping | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
4 | Structural Installation - Materials | 6420 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2889 | 2889 | 642 |  |  |  |  | 6420
5 | Structural Installation - Labor | 140952 |  | 0 | 0 | 0 | 0 | 0 | 0 | 63428.4 | 63428.4 | 14095.2 |  |  |  |  | 140952
6 | Heavy Equipment Rentals | 10500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4725 | 4725 | 1050 |  |  |  |  | 10500
7 | Mechanical/ Electric Installation - Materials | 247913 |  | 0 | 99165.2 | 0 | 0 | 0 | 0 | 74373.9 | 74373.9 | 24791.3 |  |  |  |  | 272704.3
8 | Mechanical/ Electric Installation - Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
9 | Structural Engineering | 55000 |  | 0 | 0 | 27500 | 0 | 0 | 0 | 0 | 27500 | [5 empty] | 55000
10 | Electrical Engineering | 21500 |  | 0 | 0 | 10750 | 0 | 0 | 0 | 0 | 10750 | [5 empty] | 21500
11 | Misc. Electrical Material (Panels, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
12 | Misc. Installation Material (Hoists, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
13 | CMS - Hardware | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
14 | CMS - Labor | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
15 | Scoring Equipment (OES, Etc.) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
16 | SG&A - Project Management Fees | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
17 | Travel | 30000 |  | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 9000 | 3000 |  |  |  |  | 30000
18 | Service & Warranty Requirements | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
19 | Graphic Design Services | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
20 | Bond | 74077.925 |  | 0 |  | 66670.1325 | 0 | 0 | 0 | 0 | 0 | 7407.7925 |  |  |  |  | 74077.925
21 | Taxes | 71382.6632 |  | 0 | 0 | 0 | 0 | 0 | 21414.799 | 21414.799 | 21414.799 | 7138.2663 |  |  |  |  | 71382.6632
Monthly Total COR |  | 760965.5882 |  | 0 | 140453.2 | 104920.1325 | 30966 | 0 | 30414.799 | 196475.099 | 214081.099 | 68446.5588 | 0 | 0 | 0 | 0 | 785756.8882
Monthly Gross Profit |  |  |  | 0 | -140453.2 | -12750 | 20034 | 467461.0556 | 53624 | -28397.501 | -102916.9846 | -68446.5588 | 0 | 0 | 0 | 0 | 188154.8111
Project Cash Flow |  |  |  | 0 | -140453.2 | -153203.2 | -133169.2 | 334291.8556 | 387915.8556 | 359518.3545 | 256601.3699 | 188154.8111 | 188154.8111 | 188154.8111 | 188154.8111 | 188154.8111
Formulas:
Product Shipping = DATE(YEAR([Contract Signed]),MONTH([Contract Signed])+1,DAY([Contract Signed]))
Substantial Completion = DATE(YEAR([Product Shipping]),MONTH([Product Shipping])+1,DAY([Product Shipping]))
Sign Off = DATE(YEAR([Substantial Completion]),MONTH([Substantial Completion])+1,DAY([Substantial Completion]))

## Install Margin Analysis
Project Name: Union Station
2026-02-03
Revised By: MRH
Union Station LED Displays | Cost | Selling Price | Margin $ | Margin %
Structural Material | 6420 | 7133.3333 | 713.3333 | 10%
LED and Structural Labor and Installation | 151452 | 168280 | 16828 | 10%
Electrical and Low Voltage Labor and Materials | 247913 | 275458.8889 | 27545.8889 | 10%
Structural Material | 3074 | 3415.5556 | 341.5556 | 10%
LED and Structural Labor and Installation | 37760 | 41955.5556 | 4195.5556 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Structural Material | 3193 | 3547.7778 | 354.7778 | 10%
LED and Structural Labor and Installation | 34547 | 38385.5556 | 3838.5556 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Structural Material | 3121 | 3467.7778 | 346.7778 | 10%
LED and Structural Labor and Installation | 33102 | 36780 | 3678 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Structural Material | 3848 | 4275.5556 | 427.5556 | 10%
LED and Structural Labor and Installation | 44908 | 49897.7778 | 4989.7778 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Structural Material | 2776 | 3084.4444 | 308.4444 | 10%
LED and Structural Labor and Installation | 26014 | 28904.4444 | 2890.4444 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Structural Material | 4247 | 4718.8889 | 471.8889 | 10%
LED and Structural Labor and Installation | 54461 | 60512.2222 | 6051.2222 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Project Management, General Conditions, Travel & Expenses | 30000 | 33333.3333 | 3333.3333 | 10%
Submittals, Engineering, and Permits | 91500 | 101666.6667 | 10166.6667 | 10%
Two Years Parts and Beyond Simple Component Replacement Warranty | Included | Included
| 1485286 | 1650317.7778 | 165031.7778 | 10%
TAX | 6% | 74077.925
BOND | 2.5% | 71382.6632
SUB TOTAL (BID FORM) |  | 1795778.366 | 165031.7778 | 9.19%

## Margin Analysis
Project Name: Union Station
2026-02-03
Revised By: MRH
Union Station LED Displays | Cost | Selling Price | Margin $ | Margin %
Digital Dios - 46" Diagnol - 2.5mm (QTY 6) | 103220 | 396975 | 293755 | 74%
Structural Material | 6420 | 7133.3333 | 713.3333 | 10%
LED and Structural Labor and Installation | 151452 | 168280 | 16828 | 10%
Electrical and Low Voltage Labor and Materials | 247913 | 275458.8889 | 27545.8889 | 10%
Escalator Bulkhead - 3.15'h X 12.60'w - 2.5mm (QTY 2) | 59071 | 77585 | 18514 | 23.86%
Structural Material | 3074 | 3415.5556 | 341.5556 | 10%
LED and Structural Labor and Installation | 37760 | 41955.5556 | 4195.5556 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Commuter Corridor Digital Spectaculars (Screen B11) - 7.06'h X 16.54'w - 2.5mm (QTY 1) | 99050 | 123812.5 | 24762.5 | 20%
Structural Material | 3193 | 3547.7778 | 354.7778 | 10%
LED and Structural Labor and Installation | 34547 | 38385.5556 | 3838.5556 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Commuter Corridor Digital Spectaculars (Screen B10) - 7.06'h X 14.17'w - 2.5mm (QTY 1) | 90645 | 113306.25 | 22661.25 | 20%
Structural Material | 3121 | 3467.7778 | 346.7778 | 10%
LED and Structural Labor and Installation | 33102 | 36780 | 3678 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Commuter Corridor Digital Spectaculars (Screen B9) - 7.06'h X 23.62'w - 2.5mm (QTY 1) | 132670 | 165837.5 | 33167.5 | 20%
Structural Material | 3848 | 4275.5556 | 427.5556 | 10%
LED and Structural Labor and Installation | 44908 | 49897.7778 | 4989.7778 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Commuter Corridor Digital Spectaculars (Screen B8) - 6.30'h X 12.26'w - 2.5mm (QTY 1) | 62068 | 77585 | 15517 | 20%
Structural Material | 2776 | 3084.4444 | 308.4444 | 10%
LED and Structural Labor and Installation | 26014 | 28904.4444 | 2890.4444 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Commuter Corridor Digital Spectaculars (Screen B12) - 7.06'h X 35.5'w - 2.5mm (QTY 1) | 199910 | 249887.5 | 49977.5 | 20%
Structural Material | 4247 | 4718.8889 | 471.8889 | 10%
LED and Structural Labor and Installation | 54461 | 60512.2222 | 6051.2222 | 10%
Electrical and Low Voltage Labor and Materials | 117825 | 130916.6667 | 13091.6667 | 10%
Project Management, General Conditions, Travel & Expenses | 30000 | 33333.3333 | 3333.3333 | 10%
Submittals, Engineering, and Permits | 91500 | 101666.6667 | 10166.6667 | 10%
Two Years Parts and Beyond Simple Component Replacement Warranty | Included | Included
| 2231920 | 2855306.5278 | 623386.5278 | 21.83%
TAX | 6% | 74077.925
BOND | 2.5% | 71382.6632
SUB TOTAL (BID FORM) |  | 3000767.116 | 623386.5278 | 20.77%
| 954863 | 294047 | 660816
350000
60000

## Margin Analysis (CMS Only) (hidden)
Project Name: MLSE - Scotiabank Arena - LiveSync CMS
Revision Date: May 6, 2024
Revised By: JSR
Union Station LED Displays | Cost | Selling Price | Margin $ | Margin %
Digital Dios - 46" Diagnol - 2.5mm (QTY 6) | 103220 | 396975 | 293755 | 74%
Structural Materials Section | 6420 | 7133.3333 | 713.3333 | 10%
Structural Labor Section | 151452 | 168280 | 16828 | 10%
Electrical and Data Subcontracting | 247913 | 275458.8889 | 27545.8889 | 10%
Project Management, General Conditions, Travel & Expenses | 30000 | 33333.3333 | 3333.3333 | 10%
Graphics/Design | 0 | 0 | 0 | 0%
Submittals, Engineering, and Permits | 91500 | 101666.6667 | 10166.6667 | 10%
Content Manangement System Equipment, Installation, and Commissioning
Five Years Parts and Beyond Simple Compenent Replacement Warranty | 0 | 0 | 0 | 0%
| 630505 | 982847.2222 | 352342.2222 | 35.85%
TAX | 2% | 19656.9444
BOND | 1.33% | 13071.8681
SUB TOTAL (BID FORM) |  | 1015576.0347 | 352342.2222 | 34.69%
Alternates - Add to Cost Above | Cost | Selling Price | Margin $ | Margin %
Alternate #1: Additional Animation Graphics | 5000 | 10000 | 5000 | 50%
| 0 | 0 | 0 | #DIV/0!
| 0 | 0 | 0 | #DIV/0!

## Resp Matrix - ROM Example
Project: | Union Station
Date: | 2025-11-18
| Administrative | YES | NO
| Physical Installation | ANC | Purchaser
| ANC assumes all base building structure is to be provided by others or is exsting and is of sufficient capacity to support the proposed display systems. | Include Statement
| ANC has included removal and disposal of any existing signage and display systems that would be replaced by those systems that are part of this ROM proposal. | Include Statement
| ANC assumes reasonable access will be provided to the installation team and any unknown site conditions such as lane closures, site protection, permitting, etc is not currently in this ROM Proposal. | Include Statement
| Electrical & Data Installation | ANC | Purchaser
| ANC assumes primary power feed will be provided by others or is exisitng, within 5' of the display location with sufficient amps for ANC proposed display(s); typically 208v 3-phase. | Include Statement
| ANC assumes all secondary power distribution, which may include breaker panels, disconnects, pathway, etc may be included in this ROM Estimate | Include Statement
| ANC assumes all data pathway and cabling is provided by others or is exsting from control location to the display(s). | Include Statement
| Control System | ANC | Purchaser
| ANC has provided display processors only. Content creation studio and content delivery system is not included at this time. | Include Statement
| Training | ANC | Column1
| ANC will provide appropriate on-site operation and Maintenance Training | Included Statement
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
Perform two (2) days of control system operation.
| Perform final systems testing and commissioning. | X
| Project Close- Out | ANC | Column1
Site walk thru to conduct final inspection of punch list items with ANC
| Completion of punch list items | X
| General Conditions | YES | No
| ANC has provided a parts only warranty, excluding on-site labor, on all products consistent with the factory supplier and/or 3rd party vendor. Warranty Terms and Conditions to be defined. | Included Statement
| ANC has included installation pricing with Union labor rates and/or prevailing wage negotiation. | Included Statement
| ANC has not included bonding of any kind. | Included Statement
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | Included Statement
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | Included Statement
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance. ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | Included Statement

## LED Cost Sheet
[19 empty] | 0 |  | 20%
Union Station LED Displays
|  |  |  | BID SPEC | Active Display Size (Feet) |  | Pixel Count |  |  | Square Feet | Quantity |  | LED NIT | LED Service | [6 empty] | LED | Total
OPTION | Issue | VENDOR | PRODUCT | PITCH | H | W | H |  | W | Per Screen | of Screens | Total SQ FT | Requirement | Requirement | Cost Sq. Ft | Display Cost | FCC | Processor | Shipping | Total Cost | Margin | Price | ANC Margin | Bond Cost | Total with Bond | Selling Sq. Ft | Shipping Sale Price
Digital Dios - 46" Diagnol - 2.5mm (QTY 6) |  | LG | LSCC025 | 2.5mm | 5.54 | 6.89 | 675 | x | 840 | 38.1706 | 6 | 229.0236 | 800 | Front | 385.2005 | 88220 | 0 | 15000 | 0 | 103220 | 74% | 396975 | 293755 | 5954.625 | 402929.625 | 1733.3367 | 0
Escalator Bulkhead - 3.15'h X 12.60'w - 2.5mm (QTY 2) |  | LG | GSCF026-GP | 2.5mm | 3.28 | 11.48 | 192 | x | 1344 | 37.6544 | 2 | 75.3088 | 800 | Front | 585.2039 | 44071 | 0 | 15000 | 0 | 59071 | 23.86% | 77585 | 18514 | 1163.775 | 78748.775 | 1030.2249 | 0
Commuter Corridor Digital Spectaculars (Screen B11) - 7.06'h X 16.54'w - 2.5mm (QTY 1) |  | LG | GSCF026-GP | 2.5mm | 8.2 | 16.4 | 960 | x | 1920 | 134.48 | 1 | 134.48 | 800 | Front | 625 | 84050 | 0 | 15000 | 0 | 99050 | 20% | 123812.5 | 24762.5 | 1857.1875 | 125669.6875 | 920.6759 | 0
Commuter Corridor Digital Spectaculars (Screen B10) - 7.06'h X 14.17'w - 2.5mm (QTY 1) |  | LG | GSCF026-GP | 2.5mm | 8.2 | 14.76 | 960 | x | 1728 | 121.032 | 1 | 121.032 | 800 | Front | 625 | 75645 | 0 | 15000 | 0 | 90645 | 20% | 113306.25 | 22661.25 | 1699.5937 | 115005.8437 | 936.1677 | 0
Commuter Corridor Digital Spectaculars (Screen B9) - 7.06'h X 23.62'w - 2.5mm (QTY 1) |  | LG | GSCF026-GP | 2.5mm | 8.2 | 22.96 | 960 | x | 2688 | 188.272 | 1 | 188.272 | 800 | Front | 625 | 117670 | 0 | 15000 | 0 | 132670 | 20% | 165837.5 | 33167.5 | 2487.5625 | 168325.0625 | 880.84 | 0
Commuter Corridor Digital Spectaculars (Screen B8) - 6.30'h X 12.26'w - 2.5mm (QTY 1) |  | LG | GSCF026-GP | 2.5mm | 6.56 | 11.48 | 768 | x | 1344 | 75.3088 | 1 | 75.3088 | 800 | Front | 625 | 47068 | 0 | 15000 | 0 | 62068 | 20% | 77585 | 15517 | 1163.775 | 78748.775 | 1030.2249 | 0
Commuter Corridor Digital Spectaculars (Screen B12) - 7.06'h X 35.5'w - 2.5mm (QTY 1) |  | LG | GSCF026-GP | 2.5mm | 8.2 | 36.08 | 960 | x | 4224 | 295.856 | 1 | 295.856 | 800 | Front | 625 | 184910 | 0 | 15000 | 0 | 199910 | 20% | 249887.5 | 49977.5 | 3748.3125 | 253635.8125 | 844.6254 | 0
[5 empty] | 8.2 | 9.84 | 960 |  | 1152 | 2.7648
[5 empty] | 3.28 | 11.48 | 192 |  | 1344 | 0.64512
[5 empty] | 8.2 | 16.4 | 960 |  | 1920 | 4.608
[5 empty] | 8.2 | 14.76 | 960 |  | 1728 | 4.1472
[5 empty] | 8.2 | 22.96 | 960 |  | 2688 | 6.4512
[5 empty] | 6.56 | 11.48 | 768 |  | 1344 | 5.161
[5 empty] | 8.2 | 36.08 | 960 |  | 4224 | 20.2752
814.9488
16.5%
14.85%
23.1%
9.241%
36.3%

## Resp Matrix-Indoor Wall Example (hidden)
Project: | Whatnot Lobby
Date: | 2022-08-24
| Administrative | ANC | Purchaser
| Provide accurate architectural, structural engineering, and electrical drawings or information, including exploratory surveys to confirm existing conditions if necessary. |  | X
| Provide Payment and Performance Bond. | NA |  | Editable
| All required zoning , building, street or sidewalk closure permits, and associated costs, as required. | NA |  | Editable
| Shipping of all equipment to site. | X
| Receive, unload, and inspect all new equipment upon delivery. | X
| Provide safe storage of video equipment and control equipment in a safe, dry and secure location until installation, if required. |  | X
| Unobstructed access to equipment and control room throughout installation, until equipment is 100% operational. |  | X
| Engineering & Submittals | ANC | Purchaser
| Customer is responsible to ensure the existing structure/building is adequate, including, but not limited to, providing sealed engineering and calculations, as-builts, and other information, documentation, or enabling of exploratory work as may be required for ANC's Engineer to adequately design the display system and it's attachment to the base building. ANC assumes base building defined as plywood "backer" or similar condition. |  | X
| Provide mechanical drawings, electrical drawings, shop drawings, and equipment locations for new equipment. | X
| Engineering and certification for new equipment attachment design | X
| Provide approval of all mechanical drawings, electrical drawings, shop drawings, equipment locations, color renderings, and ad copy layouts for new equipment. |  | X
| Responsible to ensure sufficient structural integrity at points of attachment, including any modifications, additions or alterations to base building construction, as required. |  | X
| Demolition, Removal & Site Cleanup | ANC | Purchaser
| Removal of existing equipment and structural components, as required. | NA |  | Editable
| Disposal of existing equipment and structural components, as required. | NA |  | Editable
| Post installation site clean-up. | X
| Physical Installation | ANC | Purchaser
| Fabricate, deliver, and install support structure and appropriate backing for all displays, including hardware, shims and miscellaneous materials as required. | X
| Provide & Install LED components. | X
| Provide all required Floor/Site Protection, if required. |  | X | Editable
| Provide camera ready artwork for ad panels, and logos at time of order, if required. |  | X
| Electrical & Data Installation | ANC | Purchaser
| Submit electrical engineering drawings | X
| Provide (and install, if required) primary power feed within 5' of the display location with sufficient amps for ANC proposed display(s); typically 208v 3-phase. |  | X | Editable
| Provide secondary electrical panels and/or remote power control, if required. |  | X | Editable
| Installation of secondary electrical panels and/or remote power control, if required. Including all conduit, wire, and low voltage conduit & wire as may be required for the remote power control. |  | X | Editable
| Provide & Install all branch circuits necessary to LED display(s) and 120V 1-phase servicing outlets in the vicinity of the display location (if necessary). Exact locations to be coordinated with ANC and electrical contractor. |  | X | Editable
| Furnish signal cables as specified by ANC. | X |  | Editable
| Provide and install signal cable conduit, with pull string, from control location to all Equipment locations/signal termination points, as delineated in the electrical and signal drawings. |  | X | Editable
| Labor to pull signal cable (and remove existing cable), if required. | X |  | Editable
| Terminate signal cable at control system equipment and display equipment, if required. | X |  | Editable
| Mount and install data patch panel in control location and display location, if required. | X |  | Editable
| Provide high speed internet connection to control room equipment. |  | X
| Power outlets on clean dedicated circuit(s) for all control equipment required per electrical engineering within control room location. |  | X
| Control System | ANC | Purchaser
| Provide climate controlled control room for all control equipment and processing. Normal operating temperature should be between 65 and 75 degrees Fahrenheit. Normal operating humidity should be less than 80 percent non condensing. |  | X
| Supply static IP address five (5) days prior to installation. |  | X
| Provide and install signal cable conduit, with pull string, from production control location to display for LiveSync control, should remote location be desired. |  | X | Editable
| Labor to pull signal cable for LiveSync or other owner supplied control, if required. | X |  | Editable
| Third party application fees as required by the customer, i.e. RSS Feeds, etc. |  | X
| Provide computer(s) for control software. | X
| Set-up, and testing of all control equipment. | X
| Training | ANC | Purchaser
| Provide list of personnel for training five (5) days in advance. |  | X
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
| Perform two (2) days of control system operation. |  | X
| Perform final systems testing and commissioning. | X
| Project Close- Out | ANC | Purchaser
| Site walk thru to conduct final inspection of punch list items with ANC |  | X
| Completion of punch list items | X
| Project Specific Notes | YES | NO
| ANC has provided a (5) year warranty on all LED parts. | X |  | Editable
| ANC has not provided on site labor during the warranty period as part of this proposal. ANC will train facility staff to perform basic troubleshooting and simple component replacement. ANC will deploy an authorized service technician to perform all escalated service needs at and invoice for costs incurred. | X |  | Editable
| ANC has provided studio graphic creation hours as part of this proposal. |  | X | Editable
| ANC has not included a video scaler as part of the control system package. This would be required for any event utilizing live camera shoots. |  | X | Editable
| ANC has included installation pricing with Union labor rates. |  | X | Editable
| ANC has included applicable bonds. |  | X | Editable
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | X
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | X
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance . ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | X

## Resp Matrix - Pitch Example (hidden)
Project: | Portland Timbers
Date: | 2022-08-29
| Administrative | ANC | Purchaser
| Provide Payment and Performance Bond. | NA |  | Editable
| All required zoning , building, street or sidewalk closure permits, and associated costs, as required. | NA |  | Editable
| Shipping of all equipment to site. | X
| Receive, unload, and inspect all new equipment upon delivery. | X
| Provide safe storage of video equipment and control equipment in a safe, dry and secure location until installation, if required. |  | X
| Unobstructed access to equipment and control room throughout installation, until equipment is 100% operational. |  | X
| Engineering & Submittals | ANC | Purchaser
| Provide mechanical drawings, electrical drawings, shop drawings, etc as relevant to new equipment. | X
| Engineering and certification for new equipment attachment design | NA
| Provide approval of all mechanical drawings, electrical drawings, shop drawings, equipment locations, color renderings, and ad copy layouts for new equipment. |  | X
| Responsible to ensure sufficient structural integrity at points of attachment, including any modifications, additions or alterations to base building construction, as required. | NA
| Physical Installation and Services | ANC | Purchaser
| Provide and Deliver LED Displays and Novastar Display Processors. | X |  | Editable
| Utilize Existing Storage Carts/Racks and all tools and components related to storage. |  | X | Editable
| Column1 | Column2 | Column3
| Initial Setup and testing of LED components, including new Novastar Display processing. | X
| Provide all required Field/Site Protection, if required. |  | X | Editable
| Post installation site clean-up. Disposal/Use of shipping materials. |  | X
| Electrical & Data Installation | ANC | Purchaser
| Submit electrical engineering drawings | X
| Provide (and install, if required) primary power feed at the display location with sufficient amps for ANC proposed display(s). |  | X | Editable
| Provide secondary electrical panels and/or remote power control, if required. |  | X | Editable
| Installation of secondary electrical panels, branch circuits and/or remote power control, if required. Including all conduit, wire, and low voltage conduit & wire as may be required for the remote power control. |  | X | Editable
| Furnish signal cables as specified by ANC. |  | X | Editable
| Provide and install signal cable conduit, with pull string, from control location to all Equipment locations/signal termination points, as delineated in the electrical and signal drawings. |  | X | Editable
| Labor to pull signal cable (and remove existing cable), if required. |  | X | Editable
| Terminate signal cable at control system equipment and display equipment, if required. |  | X | Editable
| Mount and install data patch panel in control location and display location, if required. |  | X | Editable
| Provide high speed internet connection to control room equipment. |  | X
| Power outlets on clean dedicated circuit(s) for all control equipment required per electrical engineering within control room location. |  | X
| Control System | ANC | Purchaser
| Provide climate controlled control room for all control equipment and processing. Normal operating temperature should be between 65 and 75 degrees Fahrenheit. Normal operating humidity should be less than 80 percent non condensing. |  | X
| Supply static IP address five (5) days prior to installation. |  | X
| Provide and install signal cable conduit, with pull string, from production control location to display for LiveSync control, should remote location be desired. |  | X | Editable
| Labor to pull signal cable for owner supplied control, if required. |  | X | Editable
| Third party application fees as required by the customer, i.e. RSS Feeds, etc. |  | X
| Provide computer(s) for control software. |  | X
| Set-up, and testing of all control equipment. ANC to coordinate integration of processors with existing control system. | X | X
| Training | ANC | Purchaser
| Provide list of personnel for training five (5) days in advance. |  | X
| Provide sign off list for all training to be distributed to all parties upon completion. | X
| Perform one (1) day of maintenance training. | X
| Perform one (1) days of processing/control system operation. | X
| Perform final systems testing and commissioning. | X | X
| Project Close- Out | ANC | Purchaser
| Site walk thru to conduct final inspection of punch list items with ANC |  | X
| Completion of punch list items | X
| Project Specific Notes | YES | NO
| ANC has provided a three (3) year warranty on all LED parts. | X |  | Editable
| ANC has not provided on site labor during the warranty period as part of this proposal. ANC will train facility staff to perform basic troubleshooting and simple component replacement. ANC will deploy an authorized service technician to perform all escalated service needs at and invoice for costs incurred. | X |  | Editable
| ANC has provided studio graphic creation hours as part of this proposal. |  | X | Editable
| ANC has included a video scaler as part of the control system package. This would be required for any event utilizing live camera shoots. |  | X | Editable
| ANC has included installation pricing with Union labor rates. |  | X | Editable
| ANC has included applicable bonds. |  | X | Editable
| ANC has not included any tax in the proposal. Any and all sales and use taxes, including, but not limited to, any import or associated duties, fees, tariffs as well other excises and other charges, including without limitation VAT/Sales Tax, (“collectively referred to as Government Charges”) now or henceforth levied on any date in connection with the sale of the LED System shall be the full responsibility of the Purchaser. Purchaser shall reimburse ANC for any and all Government Charges ANC may advance on Purchaser’s behalf. Purchaser acknowledges that neither ANC nor Purchaser may have advance knowledge of such Government Charges. ANC has excluded any and all taxes from the pricing in the enclosed proposal. | X
| Shipping (Ocean Freight Shipping) included in quote at current shipping pricing. Shipping pricing is subject to change due to continued global impacts of the Covid pandemic. Any increase in costs will be responsibility of Purchaser. Current Ocean Freight timelines are approximately 6 weeks. Current Air Freight timelines are approximately 2 weeks. | X
| The Purchaser acknowledges that amidst the duration of the Covid-19 pandemic (“Pandemic”) and thereafter for some undefined period of time, there may be consequences of the Pandemic or adverse market conditions (whether or not sudden or unpredictable) that could render either party’s performance . ANC shall not be responsible for any additional compensation hereunder or lost revenues or profits, damages, costs, or overhead incurred by the Purchaser relating to or arising out of (I) breakdowns in commercial negotiations with equipment or parts’ suppliers; (ii) delays in shipping or manufacturing or the availability of LED or LCD equipment or parts during the Term (iii) delays in third-party contractor obligations not under ANC’s control whose work precedes ANC’s obligations hereunder; (iv) Pandemic related closures of facilities or factories or contractors, whether domestic or international, or (v) employee unavailability, staffing shortages, shutdowns, postponements, or cancellations relating to or arising out of the Pandemic, whether due to illness, travel restrictions or Events of Force Majeure. | X

## Form
Updated on Sept 10, 2024
Prepared by:
Project: | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station | Union Station
Display Name (Use): | Digital Dios - 46" Diagnol - 2.5mm (QTY 6) | Escalator Bulkhead - 3.15'h X 12.60'w - 2.5mm | Commuter Corridor Bulkhead - 4'h X 16'w - 2.5mm | Commuter Corridor TC1 - 7.68'h X 14.29'w - 2.5mm | Commuter Corridor TC3 - 7.67'h X 14.29'w - 2.5mm | Commuter Corridor TC5 - 7.5'h X 24.91'w - 2.5mm | Commuter Corridor TC6 - 7.5'h X 21.71'w - 2.5mm | Commuter Corridor TC8 - 7.5'h X 16.29'w - 2.5mm | Commuter Corridor TC9 - 7.5'h X 18.63'w - 2.5mm | Commuter Corridor TC10 - 7.5'h X 18.75'w - 2.5mm | Commuter Corridor TC11 - 7.58'h X 21.29'w - 2.5mm | Commuter Corridor TC12 - 7.58'h X 18.79'w - 2.5mm | Commuter Corridor Digital Spectaculars (Screen B11) - 7.06'h X 16.54'w - 2.5mm | Commuter Corridor Digital Spectaculars (Screen B10) - 7.06'h X 14.17'w - 2.5mm | Commuter Corridor Digital Spectaculars (Screen B9) - 7.06'h X 23.62'w - 2.5mm | Commuter Corridor Digital Spectaculars (Screen B8) - 6.30'h X 12.26'w - 2.5mm | Commuter Corridor Digital Spectaculars (Screen B12) - 7.06'h X 35.5'w - 2.5mm | Metro Level Wall Wrap (Screen B12) - 10.5'h X 17.25'w - 2.5mm
Facility: |  | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Commuter Corridor | Food Court
Drawing Reference: | Page 2 | Page 8 | Page 10 | Page 11 | Page 12 | Page 13 | Page 14 | Page 15 | Page 16 | Page 17 | Page 18 | Page 19 | Page 20 | Page 21 | Page 22 | Page 23 | Page 24 | Page 25
refer to Config. Item | 1.1 | 2.1 | 3.1 | 4.1 | 5.1 | 6.1 | 7.1 | 8.1 | 9.1 | 10.1 | 11.1 | 12.1 | 13.1 | 14.1 | 15.1 | 15.1 | 16.1 | 17.1
Manufacturer: | bar: Page 2 to Page 25
Model: | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Physical pixel pitch(mm): | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Virtual pixel pitch: | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Panel resolution (w) | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Panel resolution (h) | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135 | 135
Spec Width / Circumference (feet) | 23.62 | 12.6 | 16 | 14.29 | 24.79 | 24.91 | 21.71 | 16.29 | 18.63 | 18.75 | 21.29 | 18.79 | 16.54 | 14.17 | 23.62 | 12.26 | 35.5 | 35.5
Spec Height (feet) | 17.72 | 3.15 | 4 | 7.68 | 7.67 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.58 | 7.58 | 7.06 | 7.06 | 7.06 | 6.3 | 7.06 | 7.06
Spec Resolution (width) | 2879.7504 | 1536.192 | 1950.72 | 1742.2368 | 3022.3968 | 3037.0272 | 2646.8832 | 1986.0768 | 2271.3696 | 2286 | 2595.6768 | 2290.8768 | 2016.5568 | 1727.6064 | 2879.7504 | 1494.7392 | 4328.16 | 4328.16
Spec Resolution (height) | 2160.4224 | 384.048 | 487.68 | 936.3456 | 935.1264 | 914.4 | 914.4 | 914.4 | 914.4 | 914.4 | 924.1536 | 924.1536 | 860.7552 | 860.7552 | 860.7552 | 768.096 | 860.7552 | 860.7552
Additional Notes | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR | M4, Front and rear access,HDR
Number of Screens | 6 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5
No. of panel (w) | 5 | 6 | 8 | 7 | 12.5 | 12.5 | 11 | 8 | 9.5 | 9.5 | 11 | 9.5 | 8.5 | 7.5 | 12 | 6 | 18 | 8.5
No. of panel (h) | 8 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 9
Total Resolution (width) | 1200 | 1440 | 1920 | 1680 | 3000 | 3000 | 2640 | 1920 | 2280 | 2280 | 2640 | 2280 | 2040 | 1800 | 2880 | 1440 | 4320 | 2040
Total Resolution (height) | 1080 | 405 | 540 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 810 | 945 | 1215
Total Resolution | 7776000 | 1166400 | 1036800 | 1587600 | 5670000 | 5670000 | 2494800 | 1814400 | 2154600 | 2154600 | 2494800 | 2154600 | 9639000 | 8505000 | 13608000 | 5832000 | 20412000 | 12393000
Total Width (feet) | 9.84 | 11.81 | 15.75 | 13.78 | 24.61 | 24.61 | 21.65 | 15.75 | 18.7 | 18.7 | 21.65 | 18.7 | 16.73 | 14.76 | 23.62 | 11.81 | 35.43 | 16.73
Total Height (feet) | 8.86 | 3.32 | 4.43 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 6.64 | 7.75 | 9.97
Area per screen (sq feet) | 87.1824 | 39.2092 | 69.7725 | 106.795 | 190.7275 | 190.7275 | 167.7875 | 122.0625 | 144.925 | 144.925 | 167.7875 | 144.925 | 129.6575 | 114.39 | 183.055 | 78.4184 | 274.5825 | 166.7981
| 523.0944 | 78.4184 | 69.7725 | 106.795 | 381.455 | 381.455 | 167.7875 | 122.0625 | 144.925 | 144.925 | 167.7875 | 144.925 | 648.2875 | 571.95 | 915.275 | 392.092 | 1372.9125 | 833.9905
Panel Weight per screen (lb) | 440 | 198 | 352 | 539 | 963 | 963 | 847 | 616 | 732 | 732 | 847 | 732 | 655 | 578 | 924 | 396 | 1386 | 842
Total Panel Weight (lb) | 2640 | 396 | 352 | 539 | 1926 | 1926 | 847 | 616 | 732 | 732 | 847 | 732 | 3275 | 2890 | 4620 | 1980 | 6930 | 4210
Max Power Consumption per screen (Watt) | 7200 | 3240 | 5760 | 8820 | 15750 | 15750 | 13860 | 10080 | 11970 | 11970 | 13860 | 11970 | 10710 | 9450 | 15120 | 6480 | 22680 | 13770
Total Max Power Consumption (Watt) | 43200 | 6480 | 5760 | 8820 | 31500 | 31500 | 13860 | 10080 | 11970 | 11970 | 13860 | 11970 | 53550 | 47250 | 75600 | 32400 | 113400 | 68850
Typical Power Consumption per screen (Watt) (Being 40% of Maxium) | 2880 | 1296 | 2304 | 3528 | 6300 | 6300 | 5544 | 4032 | 4788 | 4788 | 5544 | 4788 | 4284 | 3780 | 6048 | 2592 | 9072 | 5508
Total Typical Power Consumption (Watt) (Being 40% of Maxium) | 17280 | 2592 | 2304 | 3528 | 12600 | 12600 | 5544 | 4032 | 4788 | 4788 | 5544 | 4788 | 21420 | 18900 | 30240 | 12960 | 45360 | 27540
Processor for each Display | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K | MCTRL 4K
| 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TX Fiber convertor for each display | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RX Fiber convertor for each display | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS) | 1 (CVT4KS)
Checking Resolution (w) | 1200 | 1440 | 1920 | 1680 | 3000 | 3000 | 2640 | 1920 | 2280 | 2280 | 2640 | 2280 | 2040 | 1800 | 2880 | 1440 | 4320 | 2040
Checking Resolution (h) | 1080 | 405 | 540 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 810 | 945 | 1215
Checking no. of panel (w) | 5 | 6 | 8 | 7 | 12.5 | 12.5 | 11 | 8 | 9.5 | 9.5 | 11 | 9.5 | 8.5 | 7.5 | 12 | 6 | 18 | 8.5
Checking no. of panel (h) | 8 | 3 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 9
IM configure (w) | 10 | 12 | 16 | 14 | 25 | 25 | 22 | 16 | 19 | 19 | 22 | 19 | 17 | 15 | 24 | 12 | 36 | 17
IM configure (h) | 16 | 6 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 14 | 18
Total Panel Quantity（Standard Panel） | 240 | 36 | 32 | 49 | 175 | 175 | 77 | 56 | 66.5 | 66.5 | 77 | 66.5 | 297.5 | 262.5 | 420 | 180 | 630 | 382.5
Estimate Standard Panel Weight (kg) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Estimate Input Power (Max) (Watt) | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
Max. Brightness(After Calibration at 6500K) | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
Standard Panel Size (mm), Width | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
Standard Panel Size (mm), Height | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5 | 337.5
No. of IM per Standard Panel, Width | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
No. of IM per Standard Panel, Height | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Factor for Panel Weight | bar: Page 2 to Page 25
Factor for Power Consumption | bar: Page 2 to Page 25
Number of Spare Parts Sets | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Indoor / Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor | Outdoor
Estimated Award Date
Estimated Sales Confirmation
Estimated Ex Factory Date
Remark:
Anticipated Shipping Method | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea | by sea
Louver length (Outdoor only) | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard | standard
Additional spares beyond 2% -specify $ amount or specific quantities
Additional 100M cabling (Cat 5) Specify qty. | bar: Page 2 to Page 25
Safety Cables - If required indicate here | none | none | none | none | none | none | none | none | none | none | none | none | none | none | none | none | none | none

## Install
Project Name: Union Station
2026-02-03
Revised By: MRH
Linked Margin Assignment
|  | Install Margin | 10%
|  | Electrical Margin | 10%
|  | ANC Margin | 10%
|  | Engineering and Permits | 10%
Digital Dios - 46" Diagnol - 2.5mm (QTY 6) | Height | Width | Total Sq. Ft | QTY
| 5.54 | 6.89 | 229.0236 | 6
Structural Materials Section | ANC | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 5725.59 | 6420 | 12554 | 0% | 0 |  | 6420 | 10% | 7133.3333 | 713.3333
FABRICATE CLADDING AND TRIM | 4134 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 9859.59 | 6420 | 12554 |  | 0 |  | 6420 |  | 7133.3333 | 713.3333
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 33000 | 22482 | 0 | 0% | 0 |  | 22482 | 10% | 24980 | 2498
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 19980 | 0 | 0% | 0 |  | 19980 | 10% | 22200 | 2220
INSTALL LED DISPLAYS | 35498.658 | 59940 | 65346 | 0% | 0 |  | 59940 | 10% | 66600 | 6660
INSTALL CLADDING AND TRIM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
HEAVY EQUIPMENT | 5500 | 10500 | 12764 | 0% | 0 |  | 10500 | 10% | 11666.6667 | 1166.6667
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 25770 | 0 | 0% | 0 |  | 25770 | 10% | 28633.3333 | 2863.3333
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 2790 | 0 | 0% | 0 |  | 2790 | 10% | 3100 | 310
LOAD IN/OUT | 0 | 9990 | 0 | 0% | 0 |  | 9990 | 10% | 11100 | 1110
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 73998.658 | 151452 | 78110 |  | 0 |  | 151452 |  | 168280 | 16828
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 247913 | 0 |  | 0% | 0 |  | 247913 | 10% | 275458.8889 | 27545.8889
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 247913 | 0 | 0 |  | 0 |  | 247913 |  | 275458.8889 | 27545.8889
Escalator Bulkhead - 3.15'h X 12.60'w - 2.5mm (QTY 2) | Height | Width | Total Sq. Ft | QTY
| 3.28 | 11.48 | 75.3088 | 2
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 1882.72 | 1138 | 2418 | 0% | 0 |  | 1138 | 10% | 1264.4444 | 126.4444
FABRICATE CLADDING AND TRIM | 4305 | 1936 | 0 | 0% | 0 |  | 1936 | 10% | 2151.1111 | 215.1111
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 6187.72 | 3074 | 2418 |  | 0 |  | 3074 |  | 3415.5556 | 341.5556
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 16500 | 4260 | 0 | 0% | 0 |  | 4260 | 10% | 4733.3333 | 473.3333
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 6660 | 0 | 0% | 0 |  | 6660 | 10% | 7400 | 740
INSTALL LED DISPLAYS | 11672.864 | 13320 | 12648 | 0% | 0 |  | 13320 | 10% | 14800 | 1480
INSTALL CLADDING AND TRIM | 0 | 556 | 0 | 0% | 0 |  | 556 | 10% | 617.7778 | 61.7778
HEAVY EQUIPMENT | 13500 | 2800 | 2059 | 0% | 0 |  | 2800 | 10% | 3111.1111 | 311.1111
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 6002 | 0 | 0% | 0 |  | 6002 | 10% | 6668.8889 | 666.8889
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 832 | 0 | 0% | 0 |  | 832 | 10% | 924.4444 | 92.4444
LOAD IN/OUT | 0 | 3330 | 0 | 0% | 0 |  | 3330 | 10% | 3700 | 370
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 41672.864 | 37760 | 14707 |  | 0 |  | 37760 |  | 41955.5556 | 4195.5556
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Commuter Corridor Digital Spectaculars (Screen B11) - 7.06'h X 16.54'w - 2.5mm (QTY 1) | Height | Width | Total Sq. Ft | QTY
| 8.2 | 16.4 | 134.48 | 1
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 3362 | 1683 | 3382.49 | 0% | 0 |  | 1683 | 10% | 1870 | 187
FABRICATE CLADDING AND TRIM | 6150 | 1510 | 0 | 0% | 0 |  | 1510 | 10% | 1677.7778 | 167.7778
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 9512 | 3193 | 3382.49 |  | 0 |  | 3193 |  | 3547.7778 | 354.7778
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 11000 | 4165 | 0 | 0% | 0 |  | 4165 | 10% | 4627.7778 | 462.7778
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 6660 | 0 | 0% | 0 |  | 6660 | 10% | 7400 | 740
INSTALL LED DISPLAYS | 20844.4 | 11988 | 17251.43 | 0% | 0 |  | 11988 | 10% | 13320 | 1332
INSTALL CLADDING AND TRIM | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
HEAVY EQUIPMENT | 3500 | 2730 | 2127 | 0% | 0 |  | 2730 | 10% | 3033.3333 | 303.3333
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 4839 | 0 | 0% | 0 |  | 4839 | 10% | 5376.6667 | 537.6667
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 835 | 0 | 0% | 0 |  | 835 | 10% | 927.7778 | 92.7778
LOAD IN/OUT | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 35344.4 | 34547 | 19378.43 |  | 0 |  | 34547 |  | 38385.5556 | 3838.5556
Electrical and Data Subcontracting | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Commuter Corridor Digital Spectaculars (Screen B10) - 7.06'h X 14.17'w - 2.5mm (QTY 1) | Height | Width | Total Sq. Ft | QTY
| 8.2 | 14.76 | 121.032 | 1
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 3025.8 | 1611 | 2984.55 | 0% | 0 |  | 1611 | 10% | 1790 | 179
FABRICATE CLADDING AND TRIM | 5535 | 1510 | 0 | 0% | 0 |  | 1510 | 10% | 1677.7778 | 167.7778
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 8560.8 | 3121 | 2984.55 |  | 0 |  | 3121 |  | 3467.7778 | 346.7778
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 11000 | 3955 | 0 | 0% | 0 |  | 3955 | 10% | 4394.4444 | 439.4444
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 6245 | 0 | 0% | 0 |  | 6245 | 10% | 6938.8889 | 693.8889
INSTALL LED DISPLAYS | 18759.96 | 11240 | 15221.85 | 0% | 0 |  | 11240 | 10% | 12488.8889 | 1248.8889
INSTALL CLADDING AND TRIM | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
HEAVY EQUIPMENT | 3500 | 2730 | 2127 | 0% | 0 |  | 2730 | 10% | 3033.3333 | 303.3333
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 4767 | 0 | 0% | 0 |  | 4767 | 10% | 5296.6667 | 529.6667
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 835 | 0 | 0% | 0 |  | 835 | 10% | 927.7778 | 92.7778
LOAD IN/OUT | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 33259.96 | 33102 | 17348.85 |  | 0 |  | 33102 |  | 36780 | 3678
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Commuter Corridor Digital Spectaculars (Screen B9) - 7.06'h X 23.62'w - 2.5mm (QTY 1) | Height | Width | Total Sq. Ft | QTY
| 8.2 | 22.96 | 188.272 | 1
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 4706.8 | 2083 | 4576.31 | 0% | 0 |  | 2083 | 10% | 2314.4444 | 231.4444
FABRICATE CLADDING AND TRIM | 8610 | 1765 | 0 | 0% | 0 |  | 1765 | 10% | 1961.1111 | 196.1111
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 13316.8 | 3848 | 4576.31 |  | 0 |  | 3848 |  | 4275.5556 | 427.5556
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 11000 | 5411 | 0 | 0% | 0 |  | 5411 | 10% | 6012.2222 | 601.2222
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 8533 | 0 | 0% | 0 |  | 8533 | 10% | 9481.1111 | 948.1111
INSTALL LED DISPLAYS | 29182.16 | 16858 | 23340.17 | 0% | 0 |  | 16858 | 10% | 18731.1111 | 1873.1111
INSTALL CLADDING AND TRIM | 0 | 2498 | 0 | 0% | 0 |  | 2498 | 10% | 2775.5556 | 277.5556
HEAVY EQUIPMENT | 3500 | 2730 | 2127 | 0% | 0 |  | 2730 | 10% | 3033.3333 | 303.3333
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 6378 | 0 | 0% | 0 |  | 6378 | 10% | 7086.6667 | 708.6667
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 835 | 0 | 0% | 0 |  | 835 | 10% | 927.7778 | 92.7778
LOAD IN/OUT | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 43682.16 | 44908 | 25467.17 |  | 0 |  | 44908 |  | 49897.7778 | 4989.7778
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Commuter Corridor Digital Spectaculars (Screen B8) - 6.30'h X 12.26'w - 2.5mm (QTY 1) | Height | Width | Total Sq. Ft | QTY
| 6.56 | 11.48 | 75.3088 | 1
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 1882.72 | 1266 | 1790.73 | 0% | 0 |  | 1266 | 10% | 1406.6667 | 140.6667
FABRICATE CLADDING AND TRIM | 4305 | 1510 | 0 | 0% | 0 |  | 1510 | 10% | 1677.7778 | 167.7778
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 6187.72 | 2776 | 1790.73 |  | 0 |  | 2776 |  | 3084.4444 | 308.4444
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 11000 | 4165 | 0 | 0% | 0 |  | 4165 | 10% | 4627.7778 | 462.7778
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 4580 | 0 | 0% | 0 |  | 4580 | 10% | 5088.8889 | 508.8889
INSTALL LED DISPLAYS | 11672.864 | 7076 | 9133.11 | 0% | 0 |  | 7076 | 10% | 7862.2222 | 786.2222
INSTALL CLADDING AND TRIM | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
HEAVY EQUIPMENT | 3500 | 2030 | 2127 | 0% | 0 |  | 2030 | 10% | 2255.5556 | 225.5556
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 4413 | 0 | 0% | 0 |  | 4413 | 10% | 4903.3333 | 490.3333
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 835 | 0 | 0% | 0 |  | 835 | 10% | 927.7778 | 92.7778
LOAD IN/OUT | 0 | 1250 | 0 | 0% | 0 |  | 1250 | 10% | 1388.8889 | 138.8889
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 26172.864 | 26014 | 11260.11 |  | 0 |  | 26014 |  | 28904.4444 | 2890.4444
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Commuter Corridor Digital Spectaculars (Screen B12) - 7.06'h X 35.5'w - 2.5mm (QTY 1) | Height | Width | Total Sq. Ft | QTY
| 8.2 | 36.08 | 295.856 | 1
Structural Materials Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
FABRICATE PRIMARY STEEL | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUPPLY AND INSTALL PRIMARY PLYWOOD | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
FABRICATE SECONDARY STEEL SUBSTRUCTURE | 7396.4 | 2629 | 7162.92 | 0% | 0 |  | 2629 | 10% | 2921.1111 | 292.1111
FABRICATE CLADDING AND TRIM | 13530 | 1618 | 0 | 0% | 0 |  | 1618 | 10% | 1797.7778 | 179.7778
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PADDING (TOP/BOTTOM/SIDES) | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 20926.4 | 4247 | 7162.92 |  | 0 |  | 4247 |  | 4718.8889 | 471.8889
Structural Labor Section | Subcontractor 1 | EST | Lucent HD | 0% | Additional Contingency |  | Total Cost | Install Margin | Selling Price | Margin
REMOVAL AND DISPOSAL | 11000 | 4165 | 0 | 0% | 0 |  | 4165 | 10% | 4627.7778 | 462.7778
INSTALL SECONDARY STEEL SUBSTRUCTURE | 0 | 9160 | 0 | 0% | 0 |  | 9160 | 10% | 10177.7778 | 1017.7778
INSTALL LED DISPLAYS | 45857.68 | 24975 | 36532.44 | 0% | 0 |  | 24975 | 10% | 27750 | 2775
INSTALL CLADDING AND TRIM | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
HEAVY EQUIPMENT | 3500 | 4130 | 0 | 0% | 0 |  | 4130 | 10% | 4588.8889 | 458.8889
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
PM/GENERAL CONDITIONS/TRAVEL | 0 | 7866 | 0 | 0% | 0 |  | 7866 | 10% | 8740 | 874
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
INTERCONNECTS | 0 | 835 | 0 | 0% | 0 |  | 835 | 10% | 927.7778 | 92.7778
LOAD IN/OUT | 0 | 1665 | 0 | 0% | 0 |  | 1665 | 10% | 1850 | 185
OTHER SCOPE ITEM | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 60357.68 | 54461 | 36532.44 |  | 0 |  | 54461 |  | 60512.2222 | 6051.2222
Electrical and Data Subcontracting | Subcontractor 1 | Subcontractor 2 | Subcontractor 3 | 0% | Additional Contingency |  | Total Cost | Electrical Margin | Selling Price | Margin
Electrical - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Data - Materials | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Electrical - Labor | 117825 | 0 |  | 0% | 0 |  | 117825 | 10% | 130916.6667 | 13091.6667
Data - Labor | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
Other Scope Itemn | 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 |  | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 117825 | 0 | 0 |  | 0 |  | 117825 |  | 130916.6667 | 13091.6667
Project Management, General Conditions, Travel & Expenses | ANC Pricing | % Calculated | Other Multiplier if Needed |  |  |  | Total Cost | ANC Margin | Selling Price | Margin
Project Management | 0 | 0% | 0 | 0 | 0 | 4500 | 0 | 10% | 0 | 0
General Conditions | 0 | 0% | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Administrative & Legal | 0 | 0% | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Travel & Expenses - Linked from Worksheet | 30000 |  | 0 | 0 | 0 |  | 30000 | 10% | 33333.3333 | 3333.3333
3rd Party Technician Support | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Payment Processing Systems (Texture, etc) | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Bim Modeling | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Spare Parts Management (Job Boxes, etc that PM's Purchase on site) | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Safety Plan Documents, Badging, Etc | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Graphics/Design | 0 | 0 | 0 | 0 | 0 |  | 0 | 33.3% | 0 | 0
Installation Contingency - Typically Included in Installation Sections | 0 |  |  | 0 | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 30000 | 0 | 0 | 0 | 0 |  | 30000 |  | 33333.3333 | 3333.3333
Submittals, Engineering, and Permits | ANC Pricing | [5 empty] | Total Cost | Eng and Permit Margin | Selling Price | Margin
Structural Engineering - Specific Scope Detail? | 55000 | 0 | 0 | 0 | 0 |  | 55000 | 10% | 61111.1111 | 6111.1111
| 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Structural Certification | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Electrical Engineering - Specific Scope Detail? | 21500 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 21500 | 10% | 23888.8889 | 2388.8889
Electrical Certification | 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
Permits - Not included in subcontractor bid | 15000 | 0 | 0 | 0 | 0 |  | 15000 | 10% | 16666.6667 | 1666.6667
| 0 | 0 | 0 | 0 | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 91500 | 0 | 0 | 0 | 0 |  | 91500 |  | 101666.6667 | 10166.6667
Subtotal | [6 empty] | 375833 |  | 417592.2222 | 41759.2222
Content Management System
|  |  |  | 0% | Contingency |  | Total Cost | ANC Margin | Selling Price | Margin
Materials | 0 | 0 | 0 | 0% | 0 | 4500 | 0 | 10% | 0 | 0
Labor | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Shipping | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Related Scope Item | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Five Years Parts and Beyond Simple Compenent Replacement Warranty
| ANC Pricing |  |  | 0% |  |  | Total Cost | Margin | Selling Price | Margin
Labor Warranty - 5 Years - Beyond Simple Component Replacement | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Event Support - 3 Events | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Pre-Season Checks - 2 Seasons | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Display Cleaning - XX Cleanings | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Other Service Elements | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
Scoring, Signage and Misc. Expenses
|  |  |  | 0% | Contingency |  | Total Cost | ANC Margin | Selling Price | Margin
Materials | 0 | 0 | 0 | 0% | 0 | 4500 | 0 | 10% | 0 | 0
Labor | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Shipping | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
Related Scope Item | 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
| 0 | 0 | 0 | 0% | 0 |  | 0 | 10% | 0 | 0
SUBTOTAL | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0

## Travel (ANC) (hidden)
vSOFT
Expenses | Week | 1 | TOTALS |  |  | MASTER TRAVEL KEY
[6 empty] | City | Westchester, NY
City |  | Westchester, NY |  |  |  | Project | Community College
Project |  | Community College |  |  |  | Building | Marquee
Building |  | Marquee |  |  |  | Flight / Train Cost | 600
Stage of Job |  | Install |  |  |  | Car Rental | 125
Number of People |  | 2 |  |  |  | Taxi / Bus/ Limo | 35
Days of Travel |  | 3 |  |  |  | Gas | 30
Night of Travel |  | 4 |  |  |  | Per Diem/Day | 75
Airfare/Rail |  | 1200 | 1200 |  |  | Hotel/Night | 185
Car Rental |  | 750 | 750
Taxi/Bus/Limo |  | 210 | 210
Mileage/Gas |  | 180 | 180 |  |  | Total Project Travel | 7845
Per Diem |  | 450 | 450
Lodging/Room |  | 1480 | 1480
Daily Totals |  | 4270 | 4270
Community College
Expenses | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | TOTALS
City | [9 empty] | Total Number of Travel Days (Should Coinicde with PM on site weeks)
Project
Building
Stage of Job |  | Sales | Demolition | Primary | Secondary | Display | CMS | Closeout
Number of People |  | 1 | 1 | 0 | 1 | 1 | 1 | 0
Days of Travel |  | 1 | 3 | 0 | 3 | 4 | 1 | 0 |  | 12
Night of Travel |  | 1 | 2 | 0 | 2 | 3 | 1 | 0
Airfare/Rail |  | 600 | 600 | 0 | 600 | 600 | 600 | 0 | 3000
Car Rental |  | 125 | 375 | 0 | 375 | 500 | 125 | 0 | 1500
Taxi/Bus/Limo |  | 35 | 105 | 0 | 105 | 140 | 35 | 0 | 420
Mileage/Gas |  | 30 | 90 | 0 | 90 | 120 | 30 | 0 | 360
Per Diem |  | 75 | 225 | 0 | 225 | 300 | 75 | 0 | 900
Lodging/Room |  | 185 | 370 | 0 | 370 | 555 | 185 | 0 | 1665
Daily Totals |  | 1050 | 1765 | 0 | 1765 | 2215 | 1050 | 0 | 7845